## Planning
Sub-WP | ID | Severity | Issue | Estimate (WD) | Milestone | Assignment Reason
WP1: Critical Security & Infrastructure
1.1 | SEC-001 | CRITICAL | Hardcoded MongoDB Credentials | 2.5 |  | Security issue requiring git history cleanup to remove exposed credentials from codebase
| SEC-002 | CRITICAL | Exposed AWS Access Keys | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-003 | CRITICAL | Firebase Cloud Messaging Token Exposed | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-004 | CRITICAL | Google Maps API Key Hardcoded | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-017 | HIGH | No Secrets Management Solution | 2.5 |  | Security issue grouped by type and complexity for focused development
1.2 | BUGS-SA-012 | MEDIUM | React Query Cache Not Parameterized by Trip Inputs | 1 |  | Bug vulnerability requiring API key rotation and secrets management setup
| AWS-022 | HIGH | MFA and key rotation gaps in IAM users | 1.5 |  | AWS issue grouped by type and complexity for focused development
1.3 | SEC-005 | CRITICAL | Permissive CORS Configuration | 2.5 |  | CORS configuration issue requiring proper origin whitelisting and security headers
1.4 | SEC-006 | CRITICAL | Ineffective Rate Limiting | 2.5 |  | Rate limiting issue in API layer requiring throttle configuration
| SEC-024 | MEDIUM | No Request Size Limits | 2.5 |  | Security issue grouped by type and complexity for focused development
| PERF-DB-021 | MEDIUM | Missing Per-Endpoint Rate Limiting | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-CR-001 | CRITICAL | No API Rate Limiting | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| BUGS-DB-010 | MEDIUM | Missing Request Size Limits | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-MB-005 | MEDIUM | Throttle Rates Set to 1000/min anon and 5000/sec user | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
1.5 | PERF-DB-002 | CRITICAL | Missing Database Connection Pooling | 1.5 |  | Database connection pooling setup in Dashboard Backend to prevent connection exhaustion
| PERF-MB-005 | HIGH | Duplicate FirebaseStorageProvider | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-015 | MEDIUM | No Database Connection Pooling | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MP-013 | HIGH | No HTTP Client Configuration | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
1.6 | AWS-010 | CRITICAL | Security risk: port 22 (SSH) is open to the world on most EC2 instances. | 1.5 |  | AWS security hardening - restricting network access and closing exposed ports
| AWS-011 | CRITICAL | Database port is exposed to the internet (0.0.0.0/0) for EC2 i-0e935890cfd61f7c0. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-013 | HIGH | HTTP port 80 is open, allowing unencrypted public access. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-019 | CRITICAL | CloudTrail management events disabled | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-020 | CRITICAL | External resource sharing via IAM Access Analyzer findings | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-026 | MEDIUM | Application Load Balancers serving HTTP health checks | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-028 | HIGH | Security Groups â€“ Unrestricted Access | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-029 | HIGH | Application Load Balancer Security Group Misconfiguration | 1.5 |  | AWS issue grouped by type and complexity for focused development
WP2: Framework Upgrades & Core Performance
2.1 | SEC-010 | HIGH | Outdated Django Framework | 2.5 |  | Framework upgrade in None to address security vulnerabilities and enable new features
| PERF-DB-020 | MEDIUM | No Query Monitoring | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-024 | MEDIUM | WhiteNoise for Static Files | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-014 | HIGH | Missing Redis Cache Configuration | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
2.2 | PERF-DB-001 | MEDIUM | No Database Query Optimization | 1.5 |  | Database query optimization in Dashboard Backend to reduce query count and improve response time
| PERF-DB-003 | CRITICAL | N+1 Query in Account Serializer | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-010 | HIGH | Missing Query Optimization (only/defer) | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-011 | HIGH | Inefficient Nested Loops Over QuerySets | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-013 | HIGH | Missing Indexes on Frequently Queried Fields | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-002 | CRITICAL | Missing Database Indexes | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-003 | HIGH | N+1 in Driver Transactions | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
2.3 | PERF-DB-005 | CRITICAL | Inefficient Driver Pagination | 1.5 |  | Core database performance issue in Dashboard Backend requiring schema or query optimization
| PERF-DB-012 | HIGH | Complex Aggregation Pipeline | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-016 | MEDIUM | Date Filtering Using ObjectId Only | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-018 | MEDIUM | Unindexed Regex Queries | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-004 | HIGH | Inefficient Driver Geographic Search | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-SA-018 | LOW | Missing Favicon Fallbacks | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-019 | LOW | No Language Attribute Fallback | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-MD-002 | HIGH | Advertisement carousel never reaches last slide & leaks timer | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-DF-013 | HIGH | No focus indicators | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-030 | MEDIUM | Inconsistent font sizes | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-032 | MEDIUM | Modal backdrop z-index issues | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-037 | LOW | Print styles missing | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DB-009 | MEDIUM | Passenger pagination performs expensive regex on phone numbers | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-SA-014 | MEDIUM | Duration & Distance Rows Assume Index 0 Always Exists | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-021 | LOW | Unused CSS Class Definitions | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-DF-016 | MEDIUM | No Privacy Policy Link | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DB-015 | LOW | Missing Database Indexes | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
2.4 | PERF-DB-004 | CRITICAL | Massive Aggregation Without Pagination | 1.5 |  | Pagination implementation in Dashboard Backend to prevent memory overflow on large datasets
| PERF-DB-029 | MEDIUM | No Pagination on Transaction Exports | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-010 | MEDIUM | No Pagination on Trip Lists | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MP-011 | HIGH | No Pagination in Trip History | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MD-011 | HIGH | No pagination or virtual scrolling in trip history | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-DF-004 | HIGH | Unoptimized Firebase Queries | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DB-001 | HIGH | Driver pagination allows unbounded limit | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-002 | HIGH | GarageTrips endpoint lacks pagination | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-007 | MEDIUM | Driver pagination returns nested car/account blocks that break table layouts | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-008 | MEDIUM | Passenger pagination omits total counts so grid height jumps | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-013 | MEDIUM | Driver pagination lacks next or prev metadata | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-019 | MEDIUM | Passenger pagination returns raw ValueError traces | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-MD-006 | HIGH | Pagination guard dereferences `totalTripsCount!` before it is set | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
WP3: Authentication & Token Management
3.1 | SEC-007 | HIGH | Excessive Token Lifetime | 2.5 |  | Token lifecycle management requiring JWT refresh token implementation
| SEC-013 | HIGH | Excessive OTP Validity Period | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-022 | MEDIUM | Unlimited Concurrent Sessions | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-023 | MEDIUM | Weak Password Policy | 2.5 |  | Security issue grouped by type and complexity for focused development
| PERF-DB-006 | CRITICAL | Missing Caching Layer | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-MB-005 | HIGH | Driver phone verification deletes accounts after OTP expiry | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-006 | HIGH | Driver username verification deletes profiles | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-007 | HIGH | Passenger phone verification mirrors the destructive delete pattern | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-010 | MEDIUM | OTP email locked to 600px with no media queries | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-011 | MEDIUM | OTP email uses generic blue palette | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-012 | MEDIUM | OTP digits spaced with 8px letter-spacing | 0.5 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-013 | MEDIUM | OTP email lacks a primary action | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-015 | MEDIUM | OTP email relies on color alone to signal status | 0.5 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-017 | MEDIUM | Passenger username verification returns raw 404 text | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-022 | MEDIUM | OTP email offers no support or escalation link | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-023 | LOW | Hosted checkout inherits Mastercard theme | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-024 | LOW | OTP template mixes inconsistent heading sizes | 0.5 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-025 | LOW | OTP email lacks RTL direction support | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-026 | LOW | OTP header spacing assumes desktop margins | 0.5 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-DB-005 | HIGH | OTP validation deletes accounts after expiry | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-018 | MEDIUM | AuthTokenView logs users out mid session with generic 401 | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-MD-010 | HIGH | Token stored in plain SharedPreferences without encryption | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-014 | HIGH | Password validation regex allows weak passwords | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-DF-010 | MEDIUM | No Session Timeout Implementation | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-017 | MEDIUM | No Cookie Consent Mechanism | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DB-003 | HIGH | Weak Password Policy | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-004 | HIGH | OTP Token Expiry Too Long | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-005 | HIGH | Insufficient Session Management | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-MB-003 | HIGH | Driver Phone Verification Endpoint Enables Enumeration and Deletion | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
3.2 | SEC-008 | HIGH | Authentication Tokens in localStorage | 2.5 |  | Session security requiring httpOnly cookie implementation to prevent XSS attacks
| BUGS-DF-009 | MEDIUM | Language Selection Stored in localStorage Without Validation | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
3.3 | BUGS-DF-007 | MEDIUM | No CSRF Protection Visible | 1 |  | CSRF protection implementation requiring token validation on state-changing requests
| BUGS-DB-006 | HIGH | Missing CSRF Token Validation | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
3.4 | SEC-009 | HIGH | No Multi-Factor Authentication | 2.5 |  | Multi-factor authentication implementation for enhanced account security
WP4: Performance Optimization
4.1 | PERF-DB-009 | HIGH | Excel Export Loads All Data Into Memory | 1.5 |  | Medium-priority performance optimization in Dashboard Backend
| PERF-DB-015 | MEDIUM | Missing Query Result Caching | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-017 | LOW | Print Statements in Production | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-019 | MEDIUM | Large Serializer Depth | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-023 | LOW | No HTTP/2 Support Verification | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-030 | MEDIUM | Redundant Serializer Database Queries | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-031 | LOW | Excessive Debug Print Statements | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-006 | MEDIUM | Inefficient Promo Code Validation | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-007 | MEDIUM | Redundant Trip Fetching in Celery | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-008 | MEDIUM | No Caching for Country Settings | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-009 | HIGH | Inefficient Token Validation | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-013 | MEDIUM | Heavy Serialization Without Field Selection | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-DF-008 | MEDIUM | QueryClient Default Config | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-NTH-002 | LOW | Implement Database Query Logging | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| PERF-NTH-007 | LOW | Consider Read Replicas | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
4.2 | PERF-DB-025 | CRITICAL | Unoptimized Trip Export Pipeline | 1.5 |  | Aggregation pipeline optimization in Dashboard Backend to reduce database load
| PERF-DB-028 | MEDIUM | Inefficient Wallet Calculation | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-NTH-006 | LOW | Set Up Load Testing Pipeline | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
4.3 | PERF-DB-014 | MEDIUM | No Response Compression | 1.5 |  | Caching layer implementation in Dashboard Backend for frequently accessed data
| PERF-DB-022 | LOW | No CDN for Static/Media Files | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-001 | CRITICAL | Blocking Synchronous Trip Assignment Loop | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MB-012 | HIGH | Cache Pollution with Driver Attempts | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-DF-012 | MEDIUM | No Image Optimization | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-MP-005 | HIGH | No Image Caching Configuration | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MD-003 | HIGH | Firebase Persistence Disabled | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-012 | MEDIUM | Image Picker Without Compression | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-CR-007 | LOW | No Compression | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-NTH-008 | LOW | Implement Browser HTTP Caching Headers | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| UIUX-SA-020 | LOW | No Cache-Busting for Static Assets | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-MP-024 | LOW | No Onboarding Completion Tracking Onboarding State Not Properly Tracked | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-032 | LOW | No Onboarding Completion Tracking | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MD-008 | HIGH | Image cache never cleared during profile updates | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MP-017 | MEDIUM | Inconsistent Naming Conventions Mixed Naming Styles for Variables and Constants | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-019 | MEDIUM | DateTime Not Using Server Time Synchronization Using Device Time for Business Logic | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-026 | MEDIUM | DateTime Not Using Server Time Synchronization | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MB-007 | MEDIUM | Trip Creation Busy-Waits on Cache Without Timeout | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
4.4 | PERF-DB-007 | HIGH | Synchronous File Upload in Request | 1.5 |  | Performance monitoring and profiling setup to identify bottlenecks
| PERF-DB-008 | HIGH | No Celery for Heavy Operations | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-026 | HIGH | Synchronous SMS Sending | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-DB-027 | HIGH | Synchronous Firebase Operations | 1.5 |  | Performance issue in Dashboard Backend grouped with related issues for efficient resolution
| PERF-MB-011 | HIGH | Synchronous Firebase in Request Path | 1.5 |  | Performance issue in Mobile Backend grouped with related issues for efficient resolution
| PERF-MP-004 | MEDIUM | Synchronous Hive Initialization | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MD-004 | MEDIUM | Synchronous Wakelock in Main | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-010 | HIGH | Firebase Messaging Blocks Startup | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-015 | MEDIUM | Polyline on UI Thread | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-SA-005 | HIGH | Synchronous Geocoding Blocks UI | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-CR-004 | HIGH | No Load Testing | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-NTH-005 | LOW | Implement App Startup Profiling | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| UIUX-MD-004 | HIGH | Face ID/Touch ID toggle never appears | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
4.5.a | SEC-015 | HIGH | Insufficient Logging and Monitoring | 2.5 |  | Security monitoring telemetry for detecting and alerting on security events
4.5.b | PERF-SA-010 | LOW | Missing Performance Metrics | 1.5 |  | Frontend/application performance monitoring in Sharapp for user experience tracking
| PERF-CR-002 | CRITICAL | Firebase Cost Risk | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-CR-005 | MEDIUM | No APM Tools | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-NTH-001 | LOW | Add Application Performance Monitoring (APM) | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| PERF-NTH-003 | LOW | Add Web Vitals Tracking | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
4.5.c | UIUX-MP-023 | LOW | Missing Performance Monitoring No Production Performance Tracking | 1 |  | General monitoring setup in Mobile Passenger for operational visibility
| UIUX-MP-031 | LOW | Missing Performance Monitoring | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-DF-015 | MEDIUM | Missing Alt Text on Images | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-MP-007 | HIGH | Unsafe Context Usage in Async Callbacks `BuildContext` Used Across Async Gaps | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-DB-007 | HIGH | No Account Lockout Mechanism | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
WP5: UI/UX & Mobile
5.1.a | UIUX-MB-001 | HIGH | Payment page renders an empty layout before the checkout iframe | 1 |  | Backend UI/UX issue in Mobile Backend affecting API responses and data formatting
| UIUX-MB-003 | HIGH | Hosted checkout offers no visible cancel/back affordance | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-004 | HIGH | Checkout page lacks language, title, and instructions | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-008 | HIGH | AuthTokenView logs users out with "Invalid token" only | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-014 | MEDIUM | Error and cancel callbacks only log to console | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-016 | MEDIUM | Driver phone verification returns generic strings | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-018 | MEDIUM | Passenger email verification lacks fallback paths | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-019 | MEDIUM | Passenger login returns HTTP 422 with no guidance | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-020 | MEDIUM | Trip creation returns bare string when no drivers available | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-MB-021 | MEDIUM | Checkout markup lacks skeleton loader or progress indicator | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-DB-003 | HIGH | Transaction claim endpoint responds with plain OK | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-004 | HIGH | Checkout template misses lang, title, and labels | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-006 | HIGH | Transaction claim logging happens after the database update | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-011 | MEDIUM | Push notifications skip severity mapping | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-012 | MEDIUM | Notification copy mixes sentence case and uppercase IDs | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-014 | MEDIUM | Passenger search returns HTTP 200 with string Not Found | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-015 | MEDIUM | Error and cancel callbacks log to console instead of surfacing UI feedback | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-016 | MEDIUM | SMS encoder drops fallback language metadata | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-017 | MEDIUM | Dashboard login gives identical errors for deleted and suspended users | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-020 | MEDIUM | GarageTrips requires magic filter_type numbers with no descriptors | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-021 | LOW | TripInfoView returns ungrouped fare details | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-022 | LOW | Driver wallet export reorders columns server side | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-023 | LOW | Schedule trip reminders mix Arabic and English without locale tokens | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-024 | LOW | SMS templates omit JTNY branding | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-025 | LOW | Excel exports use default serif fonts | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-DB-026 | LOW | Auth error responses reuse backend exception text | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
5.1.b | UIUX-DF-002 | HIGH | No Code Splitting for Routes | 1 |  | Dashboard Frontend UI/UX improvement requiring component updates and styling fixes
| UIUX-DF-003 | HIGH | Missing React.memo on Frequently Re-rendered Components | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-005 | HIGH | Large Number of State Updates in Render | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-006 | HIGH | Dashboard charts overflow on small screens | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-008 | HIGH | No keyboard navigation for data grids | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-009 | HIGH | Poor color contrast in dark sections | 0.5 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-011 | HIGH | RTL layout broken for Arabic | 2 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-012 | HIGH | Sidebar state lost on refresh | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-014 | MEDIUM | No Aria Labels on Interactive Elements | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-016 | MEDIUM | No Focus Management After Modal Close | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-017 | MEDIUM | Hardcoded Strings Not Internationalized | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-018 | MEDIUM | No Empty States for Data Grids | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-019 | MEDIUM | Error Messages Too Technical | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-020 | MEDIUM | Inconsistent Button Disabled States | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-021 | MEDIUM | Inconsistent Date Formatting | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-023 | MEDIUM | Inconsistent button styles | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-024 | MEDIUM | Three different loading spinners | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-025 | MEDIUM | Table columns misaligned with headers | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-026 | MEDIUM | No breadcrumb navigation | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-027 | MEDIUM | Missing ARIA labels | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-028 | MEDIUM | Status colors not colorblind safe | 0.5 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-031 | MEDIUM | Mixed icon libraries | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-033 | MEDIUM | Deep links don't work | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-034 | LOW | No Confirmation on Destructive Actions | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-035 | LOW | Inconsistent spacing between sections | 0.5 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-038 | LOW | Brand colors inconsistent | 0.5 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-039 | LOW | Tooltip styles vary | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
5.1.c | UIUX-SA-002 | HIGH | Missing Loading States for Payment Link Creation | 1 |  | Sharapp UI/UX improvement requiring layout and interaction enhancements
| UIUX-SA-003 | HIGH | Missing rel Attributes on External Links | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-006 | HIGH | Poor contrast on status badges | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-008 | HIGH | Missing alt text for images | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-011 | MEDIUM | No keyboard shortcuts | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-012 | MEDIUM | Inconsistent component styling | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-014 | MEDIUM | No loading progress indicator | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-015 | MEDIUM | Inconsistent date formats | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-017 | MEDIUM | Inactive state unclear | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-021 | LOW | Multiple loading states | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-022 | LOW | Pixelated avatar images | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-023 | LOW | Header logo cut off | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-024 | LOW | No breadcrumbs | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-025 | LOW | Button sizes inconsistent | 0.5 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-026 | LOW | No skip navigation | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
5.2.a | UIUX-MP-001 | CRITICAL | Map search bar covers location pin | 1 |  | Mobile Passenger UI/UX issue requiring screen layout and navigation improvements
| UIUX-MP-002 | CRITICAL | Stuck in loading screen | 2 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-003 | HIGH | Hardcoded Serving Areas Instead of API Response | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-004 | HIGH | No Offline Handling or Network State Management | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-006 | HIGH | No loading state during booking | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-007 | HIGH | Color-only status indicators | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-008 | HIGH | Driver info card blocks map | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-009 | HIGH | RTL layout broken | 2 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-010 | HIGH | Insufficient contrast | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-011 | MEDIUM | Lack of Const Constructors Missing `const` Keywords on Immutable Widgets | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-012 | MEDIUM | Hardcoded Strings Not Using Localization | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-013 | MEDIUM | Misaligned car class images | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-014 | MEDIUM | Three different modal styles | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-016 | MEDIUM | Buttons too small | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-017 | MEDIUM | Overlapping price estimates | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-018 | MEDIUM | Deep link handling broken | 2 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-019 | LOW | Inconsistent Color Usage Colors Not Consistently Using Theme | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-020 | LOW | No Haptic Feedback Missing Tactile Feedback on Interactions | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-021 | LOW | No Pull-to-Refresh Functionality Data Lists Cannot Be Refreshed by User | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-022 | LOW | No Dark Mode Support Only Light Theme Implemented | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-025 | LOW | Inconsistent Color Usage | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-026 | LOW | No Haptic Feedback | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-027 | LOW | Inconsistent Border Radius Values | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-028 | LOW | No Code Splitting or Lazy Loading | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-029 | LOW | No Pull-to-Refresh Functionality | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-030 | LOW | No Dark Mode Support | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-033 | LOW | Brand colors incorrect | 0.5 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-034 | LOW | Blurry icons on high DPI | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-036 | LOW | Animation speeds vary | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-037 | LOW | Receipt layout broken | 2 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-001 | CRITICAL | Missing Error Handling in API Helper | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-002 | CRITICAL | Potential setState After Dispose | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-003 | CRITICAL | Duplicate Provider Registration | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-004 | HIGH | Missing Input Validation and Sanitization Insufficient Client-Side Input Validation | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-005 | HIGH | Excessive Use of `print()` Statements Debug Print Statements in Production Code | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-006 | HIGH | Version Mismatch Between `pubspec.yaml` and `main.dart` Hardcoded Version String Doesn't Match Package Version | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-008 | HIGH | Unhandled Null Reference Exceptions Forced Unwrapping of Nullable Types | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-009 | HIGH | Missing Input Validation and Sanitization | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-010 | HIGH | Excessive Use of print() and debugPrint() Statements | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-011 | HIGH | Version Mismatch Between pubspec.yaml and main.dart | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-012 | HIGH | Unsafe Context Usage in Async Callbacks | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-013 | HIGH | Unhandled Null Reference Exceptions | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-014 | MEDIUM | Multiple TODO Comments Left in Production Code Incomplete Implementations Marked with TODO | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-015 | MEDIUM | Commented Out Code Blocks Large Blocks of Commented Code in Source Files | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-016 | MEDIUM | Magic Numbers Throughout Codebase Hardcoded Numeric Values Without Named Constants | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-018 | MEDIUM | Large Widget Build Methods Build Methods Exceeding 500 Lines | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-020 | MEDIUM | Multiple TODO Comments Left in Production Code | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-021 | MEDIUM | Commented Out Code Blocks | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-022 | MEDIUM | Magic Numbers Throughout Codebase | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-023 | MEDIUM | Empty Catch Blocks Swallowing Exceptions | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-024 | MEDIUM | Lack of Const Constructors | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-025 | MEDIUM | Large Widget Build Methods | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-027 | LOW | Unused Import Statements Imported Packages Not Used in File | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-028 | LOW | Missing Documentation Comments No Dartdoc Comments on Public APIs | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-029 | LOW | Inconsistent File Naming Directory Name Typo and Inconsistent File Naming | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-030 | LOW | Unused Variables and Parameters Variables Declared But Never Used | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-031 | LOW | Inconsistent Async/Await Pattern Mixing `.then()` and `async/await` Styles | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-032 | LOW | Unused Import Statements | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-033 | LOW | Missing Documentation Comments | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-034 | LOW | Inconsistent File Naming | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-035 | LOW | Unused Variables and Parameters | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
| BUGS-MP-036 | LOW | Inconsistent Async/Await Pattern | 1 |  | Bug issue in Mobile Passenger grouped with related issues for efficient resolution
5.2.b | UIUX-MD-003 | HIGH | Trip type displays placeholder text | 1 |  | Mobile Driver UI/UX issue requiring interface improvements for driver workflow
| UIUX-MD-005 | HIGH | Connectivity detection disabled everywhere | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-006 | HIGH | Trip request timer overflows progress indicator | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-007 | HIGH | No validation on OCR-scanned trip kilometer values | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-009 | HIGH | No loading state when switching wallet tabs | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-010 | HIGH | Trip request dialog shows accept button only | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-012 | HIGH | No feedback when biometric authentication fails to initialize | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-013 | HIGH | No offline mode indicators or queuing | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-014 | HIGH | SOS button accessible even when not in trip | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-015 | HIGH | Firestore listener not properly cleaned up on logout | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-016 | HIGH | No confirmation dialog when changing payment method | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-017 | HIGH | Trip request modal cuts off on small screens | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-018 | HIGH | Back button exits app unexpectedly | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-019 | HIGH | Status colors unclear | 0.5 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-021 | HIGH | No voice navigation | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-022 | HIGH | Can't return from trip details | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-023 | MEDIUM | Missing empty states in wallet and trip history screens | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-024 | MEDIUM | No visual indication of trip request timeout countdown | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-025 | MEDIUM | Text too small for driving | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-026 | MEDIUM | Inconsistent iOS/Android UI | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-027 | MEDIUM | Earnings chart unreadable | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-028 | MEDIUM | Confusing tab navigation | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-029 | MEDIUM | Icon size variations | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-031 | MEDIUM | Night mode missing | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-032 | MEDIUM | Small touch targets | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-033 | MEDIUM | Overlapping elements in RTL | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-034 | LOW | Unused imports and dependencies bloat APK size | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-035 | LOW | Multiple button styles | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-036 | LOW | Outdated Material Design | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-037 | LOW | Profile image distorted | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-038 | LOW | Font inconsistency | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-001 | CRITICAL | Race condition in Firebase user data initialization | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-002 | HIGH | Background push handler never processes payload | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-003 | HIGH | Notification listeners multiply on every tap | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-004 | HIGH | Map initialization ignores denied permissions | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-005 | HIGH | Background location never switched off | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-007 | HIGH | Account deletion hidden on Android | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-008 | HIGH | Notification handler assumes `message.notification` is always present | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-009 | HIGH | Wallet calculation double-counts unclaimed transactions | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-011 | HIGH | Excessive debug logging exposes sensitive data | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-012 | HIGH | Map screen shows hardcoded Arabic text regardless of locale | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-013 | HIGH | Location stream never disposed properly | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-015 | HIGH | Missing privacy policy acknowledgment on data collection | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-016 | HIGH | Unchecked null dereference in notification handlers | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-017 | MEDIUM | Trip history loaders never recover from failures | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-018 | MEDIUM | Transaction ID display logic will crash on short UUIDs | 2.5 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-019 | MEDIUM | Memory leak from Timer in advertisement widget | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
| BUGS-MD-020 | MEDIUM | Dio timeout configuration insufficient for poor networks | 1 |  | Bug issue in Mobile Driver grouped with related issues for efficient resolution
5.3 | UIUX-SA-001 | CRITICAL | Trip info cards overflow viewport | 1 |  | Mobile app performance optimization requiring widget optimization and lazy loading
| UIUX-SA-004 | HIGH | Mobile view map unusable | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-007 | HIGH | Map doesn't resize dynamically | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-009 | MEDIUM | Poor Responsive Design for Map Height | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-010 | MEDIUM | Inconsistent Spacing and Padding | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-013 | MEDIUM | Download links overlap footer | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-SA-016 | MEDIUM | Text truncation issues | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-MP-005 | HIGH | Payment methods cut off on SE models | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-015 | MEDIUM | Time picker unusable in landscape | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MP-035 | LOW | Rating stars too close | 1 |  | UI/UX issue in Mobile Passenger grouped with related issues for efficient resolution
| UIUX-MD-001 | CRITICAL | Map controls overlap trip info | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-020 | HIGH | Chat keyboard covers input | 1 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-MD-030 | MEDIUM | Landscape mode broken | 2 |  | UI/UX issue in Mobile Driver grouped with related issues for efficient resolution
| UIUX-DF-001 | CRITICAL | Mobile view completely broken | 2 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-010 | HIGH | Map doesn't resize with viewport | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-022 | MEDIUM | Mobile Responsiveness Issues | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-029 | MEDIUM | Horizontal scroll on medium screens | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-DF-036 | LOW | Footer overlaps content | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-MB-002 | HIGH | Checkout page missing viewport meta | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
| UIUX-DB-010 | MEDIUM | Driver wallet export blocks request thread | 1 |  | UI/UX issue in Dashboard Backend grouped with related issues for efficient resolution
| UIUX-SA-005 | HIGH | No back navigation option | 1 |  | UI/UX issue in Sharapp grouped with related issues for efficient resolution
| UIUX-DF-007 | HIGH | Back button doesn't work with HashRouter | 1 |  | UI/UX issue in Dashboard Frontend grouped with related issues for efficient resolution
| UIUX-MB-009 | MEDIUM | No document title or branding on checkout page | 1 |  | UI/UX issue in Mobile Backend grouped with related issues for efficient resolution
WP6: Bugs & Code Quality
6.1 | BUGS-SA-005 | CRITICAL | Weak Comparison Operators | 1 |  | Code quality improvement in Sharapp requiring refactoring and best practices
| BUGS-SA-008 | HIGH | Hardcoded Currency Symbol | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-015 | LOW | Commented Code in Production | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-017 | LOW | Inconsistent Function Declaration Syntax | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-020 | LOW | Magic Numbers in Code | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-022 | LOW | Incomplete ESLint Configuration | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-024 | LOW | Mixed Quoting Styles | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-DF-024 | LOW | Inconsistent Import Organization | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-025 | LOW | TODO Comments Without Context | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-026 | LOW | Magic Numbers Throughout Code | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-027 | LOW | No PropTypes or TypeScript | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-028 | LOW | Inconsistent File Naming | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-MB-008 | MEDIUM | clean_drivers_data Zips Unrelated Firestore Collections | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
6.2.a | SEC-011 | HIGH | Missing Security Headers | 2.5 |  | Security hardening in None requiring validation and header configuration
| SEC-012 | HIGH | Insufficient Input Validation | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-014 | HIGH | Debug Mode Enabled | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-016 | HIGH | No Web Application Firewall | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-018 | MEDIUM | No API Versioning | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-019 | MEDIUM | No SSL Certificate Pinning | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-020 | MEDIUM | No Root/Jailbreak Detection | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-021 | MEDIUM | Insufficient File Upload Validation | 2.5 |  | Security issue grouped by type and complexity for focused development
| SEC-026 | MEDIUM | No Content Security for Stored Files | 2.5 |  | Security issue grouped by type and complexity for focused development
| PERF-DF-001 | HIGH | Insufficient Code Splitting | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-002 | HIGH | Heavy Dependencies | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-003 | CRITICAL | No Lazy Loading for Routes | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-004 | HIGH | Large MUI Bundle Without Tree-Shaking | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-005 | CRITICAL | Excessive useState/useEffect Usage | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-006 | HIGH | Missing React.memo | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-007 | HIGH | Context Providers Without Memoization | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-009 | HIGH | No Request Deduplication | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-010 | MEDIUM | Firebase Listeners Without Cleanup | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-011 | HIGH | Large DataGrid Without Virtualization | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-013 | LOW | Duplicate Charting Libraries | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-014 | MEDIUM | High Chunk Size Warning Limit | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-DF-015 | HIGH | No Build-Time Env Optimization | 1.5 |  | Performance issue in Dashboard Frontend grouped with related issues for efficient resolution
| PERF-MP-001 | CRITICAL | Too Many Root Providers | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-002 | HIGH | Duplicate FirebaseStorageProvider | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-003 | HIGH | Missing const Constructors | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-006 | MEDIUM | Heavy Dependencies | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-007 | HIGH | No Lazy Loading of Maps | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-008 | MEDIUM | Multiple Location Services | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-009 | HIGH | Provider Without Selective Rebuilds | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-010 | MEDIUM | Firestore Persistence Enabled | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-012 | MEDIUM | Flutter HTML in Chat | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MP-014 | MEDIUM | Videos in Assets | 1.5 |  | Performance issue in Mobile Passenger grouped with related issues for efficient resolution
| PERF-MD-001 | CRITICAL | MapProvider Eager Initialization | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-002 | HIGH | 14 Root ChangeNotifierProviders | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-005 | HIGH | Old SDK Version | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-006 | MEDIUM | Audio Player Resource Leak | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-007 | HIGH | Heavy Dependency Overrides | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-008 | MEDIUM | Google MLKit Text Recognition | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-009 | CRITICAL | Unoptimized Location Tracking | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-011 | HIGH | Dio Without Caching/Retry | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-013 | LOW | Device Preview in Production | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-MD-014 | HIGH | Google Maps Without Lite Mode | 1.5 |  | Performance issue in Mobile Driver grouped with related issues for efficient resolution
| PERF-SA-001 | CRITICAL | No Loading States | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-002 | CRITICAL | Firebase Listener Memory Leak | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-003 | HIGH | Google Maps Re-initialization | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-004 | HIGH | No Error Boundaries | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-006 | HIGH | No API Response Caching | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-007 | MEDIUM | Firebase Bundle Not Optimized | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-008 | MEDIUM | Map Loads Unnecessarily | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-009 | MEDIUM | No Request Debouncing | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-011 | LOW | No SSR or Progressive Enhancement | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-SA-012 | LOW | Zero Test Coverage | 1.5 |  | Performance issue in Sharapp grouped with related issues for efficient resolution
| PERF-CR-003 | HIGH | No Global Caching Strategy | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-CR-006 | MEDIUM | No Performance Budgets | 1.5 |  | Performance issue in Cross-Repo grouped with related issues for efficient resolution
| PERF-NTH-004 | LOW | Implement HTTP/2 Server Push | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| PERF-NTH-009 | LOW | Add Prefetching for Next Pages | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
| PERF-NTH-010 | LOW | Implement Adaptive Image Loading | 1.5 |  | Performance issue in Nice to Have grouped with related issues for efficient resolution
6.2.b | BUGS-SA-001 | CRITICAL | Missing Dependencies in Package.json | 1 |  | Frontend bug in Sharapp requiring error handling and state management fixes
| BUGS-SA-002 | CRITICAL | Unsafe Type Assertion with Non-null Assertion Operator | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-003 | CRITICAL | Unhandled Promise Rejection in Geocoder | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-004 | CRITICAL | Missing Image Path Leading Slash | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-006 | HIGH | No Error Boundary Implementation | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-007 | HIGH | Incomplete Error Handling in API Calls | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-009 | HIGH | Map Crashes When Destination Coordinates Are Missing | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-010 | MEDIUM | Weak Key Generation in Lists | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-011 | MEDIUM | Missing TypeScript Strict Mode Enforcement | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-013 | MEDIUM | Duplicate Firestore Listeners from Header + Page | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-016 | LOW | Console Error in Production Code | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-018 | LOW | Missing PropTypes or Runtime Validation | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-019 | LOW | Unused Import Statement | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-023 | LOW | Unused Statement in useEffect | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-SA-025 | LOW | No TypeScript Interfaces for API Responses | 1 |  | Bug issue in Sharapp grouped with related issues for efficient resolution
| BUGS-DF-001 | HIGH | No Error Boundary Implementation | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-002 | HIGH | Race Condition in Chat Message Loading | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-003 | HIGH | Memory Leak: Event Listeners Not Cleaned Up | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-004 | HIGH | Unhandled Promise Rejections | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-005 | MEDIUM | Insecure Password Reset Flow | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-006 | MEDIUM | Weak Password Requirements | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-008 | MEDIUM | Hardcoded API URLs in Chat | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-011 | MEDIUM | Axios Interceptor Initialized Multiple Times | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-012 | MEDIUM | Dependency Array Issues in useEffect | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-013 | MEDIUM | Improper Error Message Construction | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-014 | MEDIUM | Commented Out Critical Code | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-015 | MEDIUM | No Loading States for Async Operations | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-018 | MEDIUM | No Data Export Functionality | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-019 | LOW | Missing Input Length Validation | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-020 | LOW | Source Maps Enabled in Production | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-021 | LOW | Incorrect Type Checking | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-022 | LOW | Potential Null Reference Errors | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-023 | LOW | Duplicate Package Managers | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
| BUGS-DF-029 | LOW | No Account Deletion Option | 1 |  | Bug issue in Dashboard Frontend grouped with related issues for efficient resolution
6.2.c | BUGS-DB-001 | CRITICAL | Firebase Private Key Exposed | 1 |  | Backend bug in Dashboard Backend requiring API logic and data handling corrections
| BUGS-DB-002 | CRITICAL | DEBUG Mode Enabled in Dev | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-009 | MEDIUM | Missing Audit Logging for Sensitive Operations | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-011 | MEDIUM | Commented Out Code | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-012 | MEDIUM | Excessive Exception Handling with Print | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-DB-014 | LOW | Inconsistent Naming Conventions | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
| BUGS-MB-001 | CRITICAL | TripDrivePassengerView Is World-Readable | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
| BUGS-MB-002 | HIGH | Legacy settings.py.save Leaks SECRET_KEY and Debug Defaults | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
| BUGS-MB-004 | HIGH | Passenger Email Verification Endpoint is Anonymous and Destructive | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
| BUGS-MB-006 | MEDIUM | Payment Callback Endpoints Dump Query Strings to Logs | 1 |  | Bug issue in Mobile Backend grouped with related issues for efficient resolution
6.3 | BUGS-DB-008 | HIGH | PyJWT Version Vulnerability | 1 |  | Final testing and validation issue requiring comprehensive QA
| BUGS-DB-013 | MEDIUM | Requests Version Missing Security Patches | 1 |  | Bug issue in Dashboard Backend grouped with related issues for efficient resolution
WP7: Finalizing AWS & Documentation
7.1 | AWS-001 | CRITICAL | The EC2 instance i-01d9d8b30a74fae1b (mobile) is over provisioned. | 1.5 |  | AWS infrastructure optimization requiring configuration tuning
| AWS-002 | CRITICAL | The EC2 instance i-0eb1bbd45ea19979e (live2) is over provisioned. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-003 | CRITICAL | The EC2 instance i-0e935890cfd61f7c0 (live) is mis-sized. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-004 | CRITICAL | The EC2 instance i-0520151b34ebc5ef6 (staging-mobile) is over provisioned. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-005 | CRITICAL | The EC2 instance i-076e8ec11457150f6 (live2-front-staging) is over provisioned. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-006 | CRITICAL | The EC2 instance i-0d1ebd56f4b6b206c (recover-test) is over provisioned. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-007 | CRITICAL | Over provisioned EC2 resources make up ~71.4% of October 2025 cost. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-008 | CRITICAL | Too many EBS volume snapshots are retained, including very old copies. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-009 | CRITICAL | No consistent time slot is defined between backups. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-012 | HIGH | AWS Cost Optimization Hub is disabled. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-014 | HIGH | Low and inconsistent network activity indicates over-provisioned capacity. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-015 | HIGH | CPU utilization stays mostly under 10%. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-016 | HIGH | Memory usage averages below 10%. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-017 | HIGH | Very low read/write operations suggest over-provisioned storage. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-018 | HIGH | “Over-provisioned” status across all key metrics. | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-021 | MEDIUM | Unmanaged EBS/RDS snapshot lifecycle | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-023 | LOW | Unassociated Elastic IP addresses | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-024 | MEDIUM | Underutilized Amazon EBS volumes | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-025 | MEDIUM | Missing Savings Plan / RI coverage | 1.5 |  | AWS issue grouped by type and complexity for focused development
| AWS-027 | MEDIUM | Reserved Instance optimization warnings | 1.5 |  | AWS issue grouped by type and complexity for focused development