## Planning
Sub-WP | ID | Issue | Estimate (WD) | Milestone
WP1: Critical Security Remediation (IMMEDIATE)
WP1.1 | SEC-002 | Exposed AWS Access Keys | 5
| SEC-003 | Firebase Cloud Messaging Token Exposed | 4
WP1.2 | SEC-004 | Google Maps API Key Hardcoded | 4
WP1.3 | SEC-005 | Permissive CORS Configuration | 4
WP1.4 | SEC-006 | Ineffective Rate Limiting | 4
WP1.5 | SEC-001 | Hardcoded MongoDB Credentials | 4
WP2: AWS Security & Cost Optimization (URGENT)
WP2.1 | AWS-001 | The EC2 instance i-01d9d8b30a74fae1b (mobile) is over provisioned. | 2
| AWS-002 | The EC2 instance i-0eb1bbd45ea19979e (live2) is over provisioned. | 2
| AWS-003 | The EC2 instance i-0e935890cfd61f7c0 (live) is mis-sized. | 2
| AWS-004 | The EC2 instance i-0520151b34ebc5ef6 (staging-mobile) is over provisioned. | 2
| AWS-005 | The EC2 instance i-076e8ec11457150f6 (live2-front-staging) is over provisioned. | 2
| AWS-006 | The EC2 instance i-0d1ebd56f4b6b206c (recover-test) is over provisioned. | 2
| AWS-007 | Over provisioned EC2 resources make up ~71.4% of October 2025 cost. | 2
| AWS-008 | Too many EBS volume snapshots are retained, including very old copies. | 2
| AWS-009 | No consistent time slot is defined between backups. | 2
| AWS-010 | Security risk: port 22 (SSH) is open to the world on most EC2 instances. | 2
| AWS-011 | Database port is exposed to the internet (0.0.0.0/0) for EC2 i-0e935890cfd61f7c0. | 2
| AWS-019 | CloudTrail management events disabled | 3
| AWS-020 | External resource sharing via IAM Access Analyzer findings | 3
| AWS-022 | MFA and key rotation gaps in IAM users | 2
| AWS-028 | Security Groups – Unrestricted Access | 1.5
| AWS-029 | Application Load Balancer Security Group Misconfiguration | 1.5
WP2.2 | AWS-012 | AWS Cost Optimization Hub is disabled. | 1.5
| AWS-027 | Reserved Instance optimization warnings | 1
WP2.3 | AWS-013 | HTTP port 80 is open, allowing unencrypted public access. | 1.5
| AWS-014 | Low and inconsistent network activity indicates over-provisioned capacity. | 1.5
| AWS-015 | CPU utilization stays mostly under 10%. | 1.5
| AWS-016 | Memory usage averages below 10%. | 1.5
| AWS-017 | Very low read/write operations suggest over-provisioned storage. | 1.5
| AWS-018 | “Over-provisioned” status across all key metrics. | 1.5
| AWS-021 | Unmanaged EBS/RDS snapshot lifecycle | 1
| AWS-023 | Unassociated Elastic IP addresses | 0.5
| AWS-024 | Underutilized Amazon EBS volumes | 1
| AWS-025 | Missing Savings Plan / RI coverage | 1
| AWS-026 | Application Load Balancers serving HTTP health checks | 1
WP3: Framework Upgrades & Database Foundation (HIGH)
WP3.2 | PERF-DB-002 | Missing Database Connection Pooling | 4
| PERF-MB-015 | No Database Connection Pooling | 1.5
WP3.3 | PERF-DB-013 | Missing Indexes on Frequently Queried Fields | 2
| PERF-MB-002 | Missing Database Indexes | 3
WP3.4 | PERF-DB-003 | N+1 Query in Account Serializer | 4
| PERF-MB-003 | N+1 in Driver Transactions | 3
WP3.5 | PERF-DB-004 | Massive Aggregation Without Pagination | 4
| PERF-DB-005 | Inefficient Driver Pagination | 4
| PERF-MP-011 | No Pagination in Trip History | 3
WP4: Authentication & Session Security (HIGH)
WP4.1 | SEC-007 | Excessive Token Lifetime | 2
| SEC-008 | Authentication Tokens in localStorage | 4
WP4.4 | SEC-009 | No Multi-Factor Authentication | 4
WP4.5 | SEC-013 | Excessive OTP Validity Period | 2
WP5: Critical Performance Issues (HIGH)
WP5.1 | PERF-DB-006 | Missing Caching Layer | 4
| PERF-DB-007 | Synchronous File Upload in Request | 2
| PERF-DB-008 | No Celery for Heavy Operations | 2
| PERF-DB-009 | Excel Export Loads All Data Into Memory | 2
| PERF-DB-010 | Missing Query Optimization (only/defer) | 2
| PERF-DB-011 | Inefficient Nested Loops Over QuerySets | 2
| PERF-DB-012 | Complex Aggregation Pipeline | 2
| PERF-DB-025 | Unoptimized Trip Export Pipeline | 4
| PERF-DB-026 | Synchronous SMS Sending | 2
| PERF-DB-027 | Synchronous Firebase Operations | 2
WP5.2 | PERF-MB-001 | Blocking Synchronous Trip Assignment Loop | 3
| PERF-MB-004 | Inefficient Driver Geographic Search | 2
| PERF-MB-005 | Duplicate FirebaseStorageProvider | 3
| PERF-MB-009 | Inefficient Token Validation | 2
| PERF-MB-011 | Synchronous Firebase in Request Path | 2
| PERF-MB-012 | Cache Pollution with Driver Attempts | 2
| PERF-MB-014 | Missing Redis Cache Configuration | 2
WP5.3 | PERF-DF-001 | Insufficient Code Splitting | 2
| PERF-DF-002 | Heavy Dependencies | 2
| PERF-DF-003 | No Lazy Loading for Routes | 3
| PERF-DF-004 | Large MUI Bundle Without Tree-Shaking | 2
| PERF-DF-005 | Excessive useState/useEffect Usage | 3
| PERF-DF-006 | Missing React.memo | 2
| PERF-DF-007 | Context Providers Without Memoization | 2
| PERF-DF-009 | No Request Deduplication | 2
| PERF-DF-011 | Large DataGrid Without Virtualization | 2
| PERF-DF-015 | No Build-Time Env Optimization | 2
WP5.4 | PERF-MP-001 | Too Many Root Providers | 3
| PERF-MP-002 | Duplicate FirebaseStorageProvider | 2
| PERF-MP-003 | Missing const Constructors | 2
| PERF-MP-005 | No Image Caching Configuration | 2
| PERF-MP-007 | No Lazy Loading of Maps | 2
| PERF-MP-009 | Provider Without Selective Rebuilds | 2
| PERF-MP-013 | No HTTP Client Configuration | 3
WP5.5 | PERF-MD-001 | MapProvider Eager Initialization | 3
| PERF-MD-002 | 14 Root ChangeNotifierProviders | 2
| PERF-MD-003 | Firebase Persistence Disabled | 2
| PERF-MD-005 | Old SDK Version | 2
| PERF-MD-007 | Heavy Dependency Overrides | 2
| PERF-MD-009 | Unoptimized Location Tracking | 4
| PERF-MD-010 | Firebase Messaging Blocks Startup | 2
| PERF-MD-011 | Dio Without Caching/Retry | 2
| PERF-MD-014 | Google Maps Without Lite Mode | 2
WP5.6 | PERF-SA-001 | No Loading States | 3
| PERF-SA-002 | Firebase Listener Memory Leak | 3
| PERF-SA-003 | Google Maps Re-initialization | 2
| PERF-SA-004 | No Error Boundaries | 2
| PERF-SA-005 | Synchronous Geocoding Blocks UI | 2
| PERF-SA-006 | No API Response Caching | 2
WP5.7 | PERF-CR-001 | No API Rate Limiting | 3
| PERF-CR-002 | Firebase Cost Risk | 3
| PERF-CR-003 | No Global Caching Strategy | 2
| PERF-CR-004 | No Load Testing | 2
WP6: Critical UI/UX & User-Facing Bugs (MEDIUM)
WP6.1 | UIUX-SA-001 | Trip info cards overflow viewport | 2
| UIUX-SA-002 | Missing Loading States for Payment Link Creation | 1.5
| UIUX-SA-003 | Missing rel Attributes on External Links | 1.5
| UIUX-SA-004 | Mobile view map unusable | 1.5
| UIUX-SA-005 | No back navigation option | 1.5
| UIUX-SA-006 | Poor contrast on status badges | 1.5
| UIUX-SA-007 | Map doesn't resize dynamically | 1.5
| UIUX-SA-008 | Missing alt text for images | 1.5
WP6.10 | BUGS-DF-001 | No Error Boundary Implementation | 2
| BUGS-DF-002 | Race Condition in Chat Message Loading | 1.5
| BUGS-DF-003 | Memory Leak: Event Listeners Not Cleaned Up | 1.5
| BUGS-DF-004 | Unhandled Promise Rejections | 1.5
WP6.11 | BUGS-DB-001 | Firebase Private Key Exposed | 2
| BUGS-DB-002 | DEBUG Mode Enabled in Dev | 2
| BUGS-DB-003 | Weak Password Policy | 1.5
| BUGS-DB-004 | OTP Token Expiry Too Long | 1.5
| BUGS-DB-005 | Insufficient Session Management | 2
| BUGS-DB-006 | Missing CSRF Token Validation | 1.5
| BUGS-DB-007 | No Account Lockout Mechanism | 2
| BUGS-DB-008 | PyJWT Version Vulnerability | 1.5
WP6.12 | BUGS-MB-001 | TripDrivePassengerView Is World-Readable | 2
| BUGS-MB-002 | Legacy settings.py.save Leaks SECRET_KEY and Debug Defaults | 1.5
| BUGS-MB-003 | Driver Phone Verification Endpoint Enables Enumeration and Deletion | 1.5
| BUGS-MB-004 | Passenger Email Verification Endpoint is Anonymous and Destructive | 1.5
WP6.2 | UIUX-MD-001 | Map controls overlap trip info | 2
| UIUX-MD-002 | Advertisement carousel never reaches last slide & leaks timer | 1.5
| UIUX-MD-003 | Trip type displays placeholder text | 1.5
| UIUX-MD-004 | Face ID/Touch ID toggle never appears | 1.5
| UIUX-MD-005 | Connectivity detection disabled everywhere | 1.5
| UIUX-MD-006 | Trip request timer overflows progress indicator | 1.5
| UIUX-MD-007 | No validation on OCR-scanned trip kilometer values | 1.5
| UIUX-MD-008 | Image cache never cleared during profile updates | 1.5
| UIUX-MD-009 | No loading state when switching wallet tabs | 1.5
| UIUX-MD-010 | Trip request dialog shows accept button only | 1.5
| UIUX-MD-011 | No pagination or virtual scrolling in trip history | 2
| UIUX-MD-012 | No feedback when biometric authentication fails to initialize | 2
| UIUX-MD-013 | No offline mode indicators or queuing | 1.5
| UIUX-MD-014 | SOS button accessible even when not in trip | 1.5
| UIUX-MD-015 | Firestore listener not properly cleaned up on logout | 1.5
| UIUX-MD-016 | No confirmation dialog when changing payment method | 1.5
| UIUX-MD-017 | Trip request modal cuts off on small screens | 1.5
| UIUX-MD-018 | Back button exits app unexpectedly | 1.5
| UIUX-MD-019 | Status colors unclear | 1.5
| UIUX-MD-020 | Chat keyboard covers input | 1.5
| UIUX-MD-021 | No voice navigation | 1.5
| UIUX-MD-022 | Can't return from trip details | 1.5
WP6.3 | UIUX-MP-001 | Map search bar covers location pin | 2
| UIUX-MP-002 | Stuck in loading screen | 2
| UIUX-MP-003 | Hardcoded Serving Areas Instead of API Response | 1.5
| UIUX-MP-004 | No Offline Handling or Network State Management | 2
| UIUX-MP-005 | Payment methods cut off on SE models | 1.5
| UIUX-MP-006 | No loading state during booking | 1.5
| UIUX-MP-007 | Color-only status indicators | 1.5
| UIUX-MP-008 | Driver info card blocks map | 1.5
| UIUX-MP-009 | RTL layout broken | 1.5
| UIUX-MP-010 | Insufficient contrast | 1.5
WP6.4 | UIUX-DF-001 | Mobile view completely broken | 2
| UIUX-DF-002 | No Code Splitting for Routes | 1.5
| UIUX-DF-003 | Missing React.memo on Frequently Re-rendered Components | 1.5
| UIUX-DF-004 | Unoptimized Firebase Queries | 2
| UIUX-DF-005 | Large Number of State Updates in Render | 1.5
| UIUX-DF-006 | Dashboard charts overflow on small screens | 1.5
| UIUX-DF-007 | Back button doesn't work with HashRouter | 2
| UIUX-DF-008 | No keyboard navigation for data grids | 1.5
| UIUX-DF-009 | Poor color contrast in dark sections | 1.5
| UIUX-DF-010 | Map doesn't resize with viewport | 1.5
| UIUX-DF-011 | RTL layout broken for Arabic | 1.5
| UIUX-DF-012 | Sidebar state lost on refresh | 1.5
| UIUX-DF-013 | No focus indicators | 1.5
WP6.5 | UIUX-DB-001 | Driver pagination allows unbounded limit | 2
| UIUX-DB-002 | GarageTrips endpoint lacks pagination | 2
| UIUX-DB-003 | Transaction claim endpoint responds with plain OK | 1.5
| UIUX-DB-004 | Checkout template misses lang, title, and labels | 1.5
| UIUX-DB-005 | OTP validation deletes accounts after expiry | 1.5
| UIUX-DB-006 | Transaction claim logging happens after the database update | 1.5
WP6.6 | UIUX-MB-001 | Payment page renders an empty layout before the checkout iframe | 1.5
| UIUX-MB-002 | Checkout page missing viewport meta | 1.5
| UIUX-MB-003 | Hosted checkout offers no visible cancel/back affordance | 1.5
| UIUX-MB-004 | Checkout page lacks language, title, and instructions | 1.5
| UIUX-MB-005 | Driver phone verification deletes accounts after OTP expiry | 1.5
| UIUX-MB-006 | Driver username verification deletes profiles | 1.5
| UIUX-MB-007 | Passenger phone verification mirrors the destructive delete pattern | 1.5
| UIUX-MB-008 | AuthTokenView logs users out with "Invalid token" only | 1.5
WP6.7 | BUGS-SA-001 | Missing Dependencies in Package.json | 3
| BUGS-SA-002 | Unsafe Type Assertion with Non-null Assertion Operator | 2
| BUGS-SA-003 | Unhandled Promise Rejection in Geocoder | 2
| BUGS-SA-004 | Missing Image Path Leading Slash | 3
| BUGS-SA-005 | Weak Comparison Operators | 2
| BUGS-SA-006 | No Error Boundary Implementation | 2
| BUGS-SA-007 | Incomplete Error Handling in API Calls | 1.5
| BUGS-SA-008 | Hardcoded Currency Symbol | 1.5
| BUGS-SA-009 | Map Crashes When Destination Coordinates Are Missing | 1.5
WP6.8 | BUGS-MD-001 | Race condition in Firebase user data initialization | 2
| BUGS-MD-002 | Background push handler never processes payload | 1.5
| BUGS-MD-003 | Notification listeners multiply on every tap | 1.5
| BUGS-MD-004 | Map initialization ignores denied permissions | 1.5
| BUGS-MD-005 | Background location never switched off | 1.5
| BUGS-MD-006 | Pagination guard dereferences `totalTripsCount!` before it is set | 2
| BUGS-MD-007 | Account deletion hidden on Android | 1.5
| BUGS-MD-008 | Notification handler assumes `message.notification` is always present | 1.5
| BUGS-MD-009 | Wallet calculation double-counts unclaimed transactions | 1.5
| BUGS-MD-010 | Token stored in plain SharedPreferences without encryption | 2
| BUGS-MD-011 | Excessive debug logging exposes sensitive data | 1.5
| BUGS-MD-012 | Map screen shows hardcoded Arabic text regardless of locale | 1.5
| BUGS-MD-013 | Location stream never disposed properly | 1.5
| BUGS-MD-014 | Password validation regex allows weak passwords | 1.5
| BUGS-MD-015 | Missing privacy policy acknowledgment on data collection | 1.5
| BUGS-MD-016 | Unchecked null dereference in notification handlers | 1.5
WP6.9 | BUGS-MP-001 | Missing Error Handling in API Helper | 3
| BUGS-MP-002 | Potential setState After Dispose | 2
| BUGS-MP-003 | Duplicate Provider Registration | 2
| BUGS-MP-004 | Missing Input Validation and Sanitization Insufficient Client-Side Input Validation | 1.5
| BUGS-MP-005 | Excessive Use of `print()` Statements Debug Print Statements in Production Code | 1.5
| BUGS-MP-006 | Version Mismatch Between `pubspec.yaml` and `main.dart` Hardcoded Version String Doesn't Match Package Version | 1.5
| BUGS-MP-007 | Unsafe Context Usage in Async Callbacks `BuildContext` Used Across Async Gaps | 1.5
| BUGS-MP-008 | Unhandled Null Reference Exceptions Forced Unwrapping of Nullable Types | 1.5
| BUGS-MP-009 | Missing Input Validation and Sanitization | 1.5
| BUGS-MP-010 | Excessive Use of print() and debugPrint() Statements | 1.5
| BUGS-MP-011 | Version Mismatch Between pubspec.yaml and main.dart | 1.5
| BUGS-MP-012 | Unsafe Context Usage in Async Callbacks | 1.5
| BUGS-MP-013 | Unhandled Null Reference Exceptions | 1.5
WP7: Medium/Low Security & Performance (MEDIUM)
WP7.1 | SEC-018 | No API Versioning | 2
| SEC-019 | No SSL Certificate Pinning | 1
| SEC-020 | No Root/Jailbreak Detection | 1
| SEC-021 | Insufficient File Upload Validation | 1
| SEC-022 | Unlimited Concurrent Sessions | 1
| SEC-023 | Weak Password Policy | 1
| SEC-024 | No Request Size Limits | 1
| SEC-025 | No Database Query Optimization | 1.5
| SEC-026 | No Content Security for Stored Files | 1
WP7.2 | PERF-DB-001 | No Database Query Optimization | 1.5
| PERF-DB-014 | No Response Compression | 1
| PERF-DB-015 | Missing Query Result Caching | 1
| PERF-DB-016 | Date Filtering Using ObjectId Only | 1
| PERF-DB-017 | Print Statements in Production | 0.5
| PERF-DB-018 | Unindexed Regex Queries | 1
| PERF-DB-019 | Large Serializer Depth | 1
| PERF-DB-020 | No Query Monitoring | 1
| PERF-DB-021 | Missing Per-Endpoint Rate Limiting | 1
| PERF-DB-022 | No CDN for Static/Media Files | 0.5
| PERF-DB-023 | No HTTP/2 Support Verification | 0.5
| PERF-DB-024 | WhiteNoise for Static Files | 1
| PERF-DB-028 | Inefficient Wallet Calculation | 1
| PERF-DB-029 | No Pagination on Transaction Exports | 1.5
| PERF-DB-030 | Redundant Serializer Database Queries | 1
| PERF-DB-031 | Excessive Debug Print Statements | 0.5
WP7.3 | PERF-MB-006 | Inefficient Promo Code Validation | 1
| PERF-MB-007 | Redundant Trip Fetching in Celery | 1
| PERF-MB-008 | No Caching for Country Settings | 1
| PERF-MB-010 | No Pagination on Trip Lists | 1.5
| PERF-MB-013 | Heavy Serialization Without Field Selection | 1
WP7.4 | PERF-DF-008 | QueryClient Default Config | 1
| PERF-DF-010 | Firebase Listeners Without Cleanup | 1
| PERF-DF-012 | No Image Optimization | 1
| PERF-DF-013 | Duplicate Charting Libraries | 0.5
| PERF-DF-014 | High Chunk Size Warning Limit | 1
WP7.5 | PERF-MP-004 | Synchronous Hive Initialization | 1
| PERF-MP-006 | Heavy Dependencies | 1
| PERF-MP-008 | Multiple Location Services | 1
| PERF-MP-010 | Firestore Persistence Enabled | 1
| PERF-MP-012 | Flutter HTML in Chat | 1
| PERF-MP-014 | Videos in Assets | 1
WP7.6 | PERF-MD-004 | Synchronous Wakelock in Main | 1
| PERF-MD-006 | Audio Player Resource Leak | 1
| PERF-MD-008 | Google MLKit Text Recognition | 1
| PERF-MD-012 | Image Picker Without Compression | 1
| PERF-MD-013 | Device Preview in Production | 0.5
| PERF-MD-015 | Polyline on UI Thread | 1
WP7.7 | PERF-SA-007 | Firebase Bundle Not Optimized | 1
| PERF-SA-008 | Map Loads Unnecessarily | 1
| PERF-SA-009 | No Request Debouncing | 1
| PERF-SA-010 | Missing Performance Metrics | 0.5
| PERF-SA-011 | No SSR or Progressive Enhancement | 0.5
| PERF-SA-012 | Zero Test Coverage | 0.5
WP8: UI/UX Improvements & Non-Critical Bugs (LOW)
WP8.1 | UIUX-SA-009 | Poor Responsive Design for Map Height | 1
| UIUX-SA-010 | Inconsistent Spacing and Padding | 1
| UIUX-SA-011 | No keyboard shortcuts | 1
| UIUX-SA-012 | Inconsistent component styling | 1
| UIUX-SA-013 | Download links overlap footer | 1
| UIUX-SA-014 | No loading progress indicator | 1
| UIUX-SA-015 | Inconsistent date formats | 1
| UIUX-SA-016 | Text truncation issues | 1
| UIUX-SA-017 | Inactive state unclear | 1
| UIUX-SA-018 | Missing Favicon Fallbacks | 0.5
| UIUX-SA-019 | No Language Attribute Fallback | 0.5
| UIUX-SA-020 | No Cache-Busting for Static Assets | 0.5
| UIUX-SA-021 | Multiple loading states | 0.5
| UIUX-SA-022 | Pixelated avatar images | 0.5
| UIUX-SA-023 | Header logo cut off | 0.5
| UIUX-SA-024 | No breadcrumbs | 0.5
| UIUX-SA-025 | Button sizes inconsistent | 0.5
| UIUX-SA-026 | No skip navigation | 0.5
WP8.10 | BUGS-DF-005 | Insecure Password Reset Flow | 1
| BUGS-DF-006 | Weak Password Requirements | 1
| BUGS-DF-007 | No CSRF Protection Visible | 1
| BUGS-DF-008 | Hardcoded API URLs in Chat | 1
| BUGS-DF-009 | Language Selection Stored in localStorage Without Validation | 1
| BUGS-DF-010 | No Session Timeout Implementation | 1.5
| BUGS-DF-011 | Axios Interceptor Initialized Multiple Times | 1
| BUGS-DF-012 | Dependency Array Issues in useEffect | 1
| BUGS-DF-013 | Improper Error Message Construction | 1
| BUGS-DF-014 | Commented Out Critical Code | 1
| BUGS-DF-015 | No Loading States for Async Operations | 1.5
| BUGS-DF-016 | No Privacy Policy Link | 1
| BUGS-DF-017 | No Cookie Consent Mechanism | 1
| BUGS-DF-018 | No Data Export Functionality | 1
| BUGS-DF-019 | Missing Input Length Validation | 0.5
| BUGS-DF-020 | Source Maps Enabled in Production | 0.5
| BUGS-DF-021 | Incorrect Type Checking | 0.5
| BUGS-DF-022 | Potential Null Reference Errors | 0.5
| BUGS-DF-023 | Duplicate Package Managers | 0.5
| BUGS-DF-024 | Inconsistent Import Organization | 0.5
| BUGS-DF-025 | TODO Comments Without Context | 0.5
| BUGS-DF-026 | Magic Numbers Throughout Code | 0.5
| BUGS-DF-027 | No PropTypes or TypeScript | 0.5
| BUGS-DF-028 | Inconsistent File Naming | 0.5
| BUGS-DF-029 | No Account Deletion Option | 0.5
WP8.11 | BUGS-DB-009 | Missing Audit Logging for Sensitive Operations | 1.5
| BUGS-DB-010 | Missing Request Size Limits | 1
| BUGS-DB-011 | Commented Out Code | 1
| BUGS-DB-012 | Excessive Exception Handling with Print | 1
| BUGS-DB-013 | Requests Version Missing Security Patches | 1
| BUGS-DB-014 | Inconsistent Naming Conventions | 0.5
| BUGS-DB-015 | Missing Database Indexes | 0.5
WP8.12 | BUGS-MB-005 | Throttle Rates Set to 1000/min anon and 5000/sec user | 1
| BUGS-MB-006 | Payment Callback Endpoints Dump Query Strings to Logs | 1
| BUGS-MB-007 | Trip Creation Busy-Waits on Cache Without Timeout | 1
| BUGS-MB-008 | clean_drivers_data Zips Unrelated Firestore Collections | 1
WP8.2 | UIUX-MD-023 | Missing empty states in wallet and trip history screens | 1
| UIUX-MD-024 | No visual indication of trip request timeout countdown | 1
| UIUX-MD-025 | Text too small for driving | 1
| UIUX-MD-026 | Inconsistent iOS/Android UI | 1
| UIUX-MD-027 | Earnings chart unreadable | 1
| UIUX-MD-028 | Confusing tab navigation | 1
| UIUX-MD-029 | Icon size variations | 1
| UIUX-MD-030 | Landscape mode broken | 1
| UIUX-MD-031 | Night mode missing | 1
| UIUX-MD-032 | Small touch targets | 1
| UIUX-MD-033 | Overlapping elements in RTL | 1
| UIUX-MD-034 | Unused imports and dependencies bloat APK size | 0.5
| UIUX-MD-035 | Multiple button styles | 0.5
| UIUX-MD-036 | Outdated Material Design | 0.5
| UIUX-MD-037 | Profile image distorted | 0.5
| UIUX-MD-038 | Font inconsistency | 0.5
WP8.3 | UIUX-MP-011 | Lack of Const Constructors Missing `const` Keywords on Immutable Widgets | 1
| UIUX-MP-012 | Hardcoded Strings Not Using Localization | 1
| UIUX-MP-013 | Misaligned car class images | 1
| UIUX-MP-014 | Three different modal styles | 1
| UIUX-MP-015 | Time picker unusable in landscape | 1
| UIUX-MP-016 | Buttons too small | 1
| UIUX-MP-017 | Overlapping price estimates | 1
| UIUX-MP-018 | Deep link handling broken | 1
| UIUX-MP-019 | Inconsistent Color Usage Colors Not Consistently Using Theme | 0.5
| UIUX-MP-020 | No Haptic Feedback Missing Tactile Feedback on Interactions | 0.5
| UIUX-MP-021 | No Pull-to-Refresh Functionality Data Lists Cannot Be Refreshed by User | 0.5
| UIUX-MP-022 | No Dark Mode Support Only Light Theme Implemented | 0.5
| UIUX-MP-023 | Missing Performance Monitoring No Production Performance Tracking | 0.5
| UIUX-MP-024 | No Onboarding Completion Tracking Onboarding State Not Properly Tracked | 0.5
| UIUX-MP-025 | Inconsistent Color Usage | 0.5
| UIUX-MP-026 | No Haptic Feedback | 0.5
| UIUX-MP-027 | Inconsistent Border Radius Values | 0.5
| UIUX-MP-028 | No Code Splitting or Lazy Loading | 0.5
| UIUX-MP-029 | No Pull-to-Refresh Functionality | 0.5
| UIUX-MP-030 | No Dark Mode Support | 0.5
| UIUX-MP-031 | Missing Performance Monitoring | 0.5
| UIUX-MP-032 | No Onboarding Completion Tracking | 0.5
| UIUX-MP-033 | Brand colors incorrect | 0.5
| UIUX-MP-034 | Blurry icons on high DPI | 0.5
| UIUX-MP-035 | Rating stars too close | 0.5
| UIUX-MP-036 | Animation speeds vary | 0.5
| UIUX-MP-037 | Receipt layout broken | 0.5
WP8.4 | UIUX-DF-014 | No Aria Labels on Interactive Elements | 1
| UIUX-DF-015 | Missing Alt Text on Images | 1
| UIUX-DF-016 | No Focus Management After Modal Close | 1
| UIUX-DF-017 | Hardcoded Strings Not Internationalized | 1.5
| UIUX-DF-018 | No Empty States for Data Grids | 1
| UIUX-DF-019 | Error Messages Too Technical | 1
| UIUX-DF-020 | Inconsistent Button Disabled States | 1
| UIUX-DF-021 | Inconsistent Date Formatting | 1
| UIUX-DF-022 | Mobile Responsiveness Issues | 1
| UIUX-DF-023 | Inconsistent button styles | 1
| UIUX-DF-024 | Three different loading spinners | 1
| UIUX-DF-025 | Table columns misaligned with headers | 1
| UIUX-DF-026 | No breadcrumb navigation | 1
| UIUX-DF-027 | Missing ARIA labels | 1
| UIUX-DF-028 | Status colors not colorblind safe | 1
| UIUX-DF-029 | Horizontal scroll on medium screens | 1
| UIUX-DF-030 | Inconsistent font sizes | 1
| UIUX-DF-031 | Mixed icon libraries | 1
| UIUX-DF-032 | Modal backdrop z-index issues | 1
| UIUX-DF-033 | Deep links don't work | 1
| UIUX-DF-034 | No Confirmation on Destructive Actions | 0.5
| UIUX-DF-035 | Inconsistent spacing between sections | 0.5
| UIUX-DF-036 | Footer overlaps content | 0.5
| UIUX-DF-037 | Print styles missing | 0.5
| UIUX-DF-038 | Brand colors inconsistent | 0.5
| UIUX-DF-039 | Tooltip styles vary | 0.5
WP8.5 | UIUX-DB-007 | Driver pagination returns nested car/account blocks that break table layouts | 1.5
| UIUX-DB-008 | Passenger pagination omits total counts so grid height jumps | 1.5
| UIUX-DB-009 | Passenger pagination performs expensive regex on phone numbers | 1.5
| UIUX-DB-010 | Driver wallet export blocks request thread | 1
| UIUX-DB-011 | Push notifications skip severity mapping | 1
| UIUX-DB-012 | Notification copy mixes sentence case and uppercase IDs | 1
| UIUX-DB-013 | Driver pagination lacks next or prev metadata | 1.5
| UIUX-DB-014 | Passenger search returns HTTP 200 with string Not Found | 1
| UIUX-DB-015 | Error and cancel callbacks log to console instead of surfacing UI feedback | 1
| UIUX-DB-016 | SMS encoder drops fallback language metadata | 1
| UIUX-DB-017 | Dashboard login gives identical errors for deleted and suspended users | 1
| UIUX-DB-018 | AuthTokenView logs users out mid session with generic 401 | 1
| UIUX-DB-019 | Passenger pagination returns raw ValueError traces | 1.5
| UIUX-DB-020 | GarageTrips requires magic filter_type numbers with no descriptors | 1
| UIUX-DB-021 | TripInfoView returns ungrouped fare details | 0.5
| UIUX-DB-022 | Driver wallet export reorders columns server side | 0.5
| UIUX-DB-023 | Schedule trip reminders mix Arabic and English without locale tokens | 0.5
| UIUX-DB-024 | SMS templates omit JTNY branding | 0.5
| UIUX-DB-025 | Excel exports use default serif fonts | 0.5
| UIUX-DB-026 | Auth error responses reuse backend exception text | 0.5
WP8.6 | UIUX-MB-009 | No document title or branding on checkout page | 1
| UIUX-MB-010 | OTP email locked to 600px with no media queries | 1
| UIUX-MB-011 | OTP email uses generic blue palette | 1
| UIUX-MB-012 | OTP digits spaced with 8px letter-spacing | 1
| UIUX-MB-013 | OTP email lacks a primary action | 1
| UIUX-MB-014 | Error and cancel callbacks only log to console | 1
| UIUX-MB-015 | OTP email relies on color alone to signal status | 1
| UIUX-MB-016 | Driver phone verification returns generic strings | 1
| UIUX-MB-017 | Passenger username verification returns raw 404 text | 1
| UIUX-MB-018 | Passenger email verification lacks fallback paths | 1
| UIUX-MB-019 | Passenger login returns HTTP 422 with no guidance | 1
| UIUX-MB-020 | Trip creation returns bare string when no drivers available | 1
| UIUX-MB-021 | Checkout markup lacks skeleton loader or progress indicator | 1
| UIUX-MB-022 | OTP email offers no support or escalation link | 1
| UIUX-MB-023 | Hosted checkout inherits Mastercard theme | 0.5
| UIUX-MB-024 | OTP template mixes inconsistent heading sizes | 0.5
| UIUX-MB-025 | OTP email lacks RTL direction support | 0.5
| UIUX-MB-026 | OTP header spacing assumes desktop margins | 0.5
WP8.7 | BUGS-SA-010 | Weak Key Generation in Lists | 1
| BUGS-SA-011 | Missing TypeScript Strict Mode Enforcement | 1
| BUGS-SA-012 | React Query Cache Not Parameterized by Trip Inputs | 1.5
| BUGS-SA-013 | Duplicate Firestore Listeners from Header + Page | 1
| BUGS-SA-014 | Duration & Distance Rows Assume Index 0 Always Exists | 1
| BUGS-SA-015 | Commented Code in Production | 0.5
| BUGS-SA-016 | Console Error in Production Code | 0.5
| BUGS-SA-017 | Inconsistent Function Declaration Syntax | 0.5
| BUGS-SA-018 | Missing PropTypes or Runtime Validation | 0.5
| BUGS-SA-019 | Unused Import Statement | 0.5
| BUGS-SA-020 | Magic Numbers in Code | 0.5
| BUGS-SA-021 | Unused CSS Class Definitions | 0.5
| BUGS-SA-022 | Incomplete ESLint Configuration | 0.5
| BUGS-SA-023 | Unused Statement in useEffect | 0.5
| BUGS-SA-024 | Mixed Quoting Styles | 0.5
| BUGS-SA-025 | No TypeScript Interfaces for API Responses | 0.5
WP8.8 | BUGS-MD-017 | Trip history loaders never recover from failures | 1
| BUGS-MD-018 | Transaction ID display logic will crash on short UUIDs | 1
| BUGS-MD-019 | Memory leak from Timer in advertisement widget | 1
| BUGS-MD-020 | Dio timeout configuration insufficient for poor networks | 1
WP8.9 | BUGS-MP-014 | Multiple TODO Comments Left in Production Code Incomplete Implementations Marked with TODO | 1.5
| BUGS-MP-015 | Commented Out Code Blocks Large Blocks of Commented Code in Source Files | 1
| BUGS-MP-016 | Magic Numbers Throughout Codebase Hardcoded Numeric Values Without Named Constants | 1
| BUGS-MP-017 | Inconsistent Naming Conventions Mixed Naming Styles for Variables and Constants | 1
| BUGS-MP-018 | Large Widget Build Methods Build Methods Exceeding 500 Lines | 1
| BUGS-MP-019 | DateTime Not Using Server Time Synchronization Using Device Time for Business Logic | 1
| BUGS-MP-020 | Multiple TODO Comments Left in Production Code | 1.5
| BUGS-MP-021 | Commented Out Code Blocks | 1
| BUGS-MP-022 | Magic Numbers Throughout Codebase | 1
| BUGS-MP-023 | Empty Catch Blocks Swallowing Exceptions | 1
| BUGS-MP-024 | Lack of Const Constructors | 1
| BUGS-MP-025 | Large Widget Build Methods | 1
| BUGS-MP-026 | DateTime Not Using Server Time Synchronization | 1
| BUGS-MP-027 | Unused Import Statements Imported Packages Not Used in File | 0.5
| BUGS-MP-028 | Missing Documentation Comments No Dartdoc Comments on Public APIs | 0.5
| BUGS-MP-029 | Inconsistent File Naming Directory Name Typo and Inconsistent File Naming | 0.5
| BUGS-MP-030 | Unused Variables and Parameters Variables Declared But Never Used | 0.5
| BUGS-MP-031 | Inconsistent Async/Await Pattern Mixing `.then()` and `async/await` Styles | 0.5
| BUGS-MP-032 | Unused Import Statements | 0.5
| BUGS-MP-033 | Missing Documentation Comments | 0.5
| BUGS-MP-034 | Inconsistent File Naming | 0.5
| BUGS-MP-035 | Unused Variables and Parameters | 0.5
| BUGS-MP-036 | Inconsistent Async/Await Pattern | 0.5