## WP
# | Work Package | Issue Count | Duration | Sub-Work Packages / Deliverables
1 | Critical Security Remediation (P0 - IMMEDIATE) | 6 | 1-2 weeks | 1.1- Clean Git History & Remove Hardcoded Credentials (2 issues) 1.2- Rotate AWS Keys, Firebase Tokens & API Keys (1 issues) 1.3- Fix CORS Configuration (1 issues) 1.4- Implement Rate Limiting (1 issues) 1.5- Other Critical Security Issues (1 issues)
2 | AWS Security & Cost Optimization (P0 - URGENT) | 29 | 2-3 weeks | 2.1- AWS Security Hardening (IAM, Security Groups, CloudTrail) (16 issues) 2.2- AWS Cost Optimization (EC2, EBS, RDS) (2 issues) 2.3- Other AWS Improvements (11 issues)
3 | Framework Upgrades & Database Foundation (P1 - HIGH) | 9 | 2-3 weeks | 3.2- Implement Database Connection Pooling (2 issues) 3.3- Add Critical Database Indexes (2 issues) 3.4- Fix Critical N+1 Queries (2 issues) 3.5- Implement Pagination Improvements (3 issues)
4 | Authentication & Session Security (P1 - HIGH) | 4 | 1-2 weeks | 4.1- Token Lifecycle Management (Access + Refresh Tokens) (2 issues) 4.2- Secure Session Storage (httpOnly Cookies) (0 issues) 4.3- CSRF Protection (0 issues) 4.4- Multi-Factor Authentication (1 issues) 4.5- Other Authentication Security (1 issues)
5 | Critical Performance Issues (P1 - HIGH) | 53 | 3-4 weeks | 5.1- Dashboard Backend - Critical Performance (10 issues) 5.2- Mobile Backend - Critical Performance (7 issues) 5.3- Dashboard Frontend - Critical Performance (10 issues) 5.4- Mobile Passenger - Critical Performance (7 issues) 5.5- Mobile Driver - Critical Performance (9 issues) 5.6- Sharapp - Critical Performance (6 issues) 5.7- Cross-Repo Critical Performance (4 issues)
6 | Critical UI/UX & User-Facing Bugs (P2 - MEDIUM) | 121 | 4-5 weeks | 6.1- Sharapp - Critical UI/UX (8 issues) 6.2- Mobile Driver - Critical UI/UX (22 issues) 6.3- Mobile Passenger - Critical UI/UX (10 issues) 6.4- Dashboard Frontend - Critical UI/UX (13 issues) 6.5- Dashboard Backend - Critical UI/UX (6 issues) 6.6- Mobile Backend - Critical UI/UX (8 issues) 6.7- Sharapp - Critical Bugs (9 issues) 6.8- Mobile Driver - Critical Bugs (16 issues) 6.9- Mobile Passenger - Critical Bugs (13 issues) 6.10- Dashboard Frontend - Critical Bugs (4 issues) 6.11- Dashboard Backend - Critical Bugs (8 issues) 6.12- Mobile Backend - Critical Bugs (4 issues)
7 | Medium/Low Security & Performance (P2 - MEDIUM) | 53 | 3-4 weeks | 7.1- Medium/Low Security Issues (9 issues) 7.2- Dashboard Backend - Medium/Low Performance (16 issues) 7.3- Mobile Backend - Medium/Low Performance (5 issues) 7.4- Dashboard Frontend - Medium/Low Performance (5 issues) 7.5- Mobile Passenger - Medium/Low Performance (6 issues) 7.6- Mobile Driver - Medium/Low Performance (6 issues) 7.7- Sharapp - Medium/Low Performance (6 issues)
8 | UI/UX Improvements & Non-Critical Bugs (P3 - LOW) | 204 | 5-6 weeks | 8.1- Sharapp - Medium/Low UI/UX (18 issues) 8.2- Mobile Driver - Medium/Low UI/UX (16 issues) 8.3- Mobile Passenger - Medium/Low UI/UX (27 issues) 8.4- Dashboard Frontend - Medium/Low UI/UX (26 issues) 8.5- Dashboard Backend - Medium/Low UI/UX (20 issues) 8.6- Mobile Backend - Medium/Low UI/UX (18 issues) 8.7- Sharapp - Medium/Low Bugs (16 issues) 8.8- Mobile Driver - Medium/Low Bugs (4 issues) 8.9- Mobile Passenger - Medium/Low Bugs (23 issues) 8.10- Dashboard Frontend - Medium/Low Bugs (25 issues) 8.11- Dashboard Backend - Medium/Low Bugs (7 issues) 8.12- Mobile Backend - Medium/Low Bugs (4 issues)