## Sheet1
Sub-WP | ID | Issue | Estimate (WD) | Milestone
WP1: Critical Security & Infrastructure
1.1 | SEC-001 | Hardcoded MongoDB Credentials |  |  | # | Work Package | Issue Count | Duration | Sub-Work Packages / Deliverables
| SEC-002 | Exposed AWS Access Keys |  |  | 1 | Critical Security & Infrastructure |  |  | 1.1- Fix all hardcoded credentials with git history cleanup
| SEC-003 | Firebase Cloud Messaging Token Exposed | [6 empty] | 1.2- Rotate all API keys and secrets
| SEC-004 | Google Maps API Key Hardcoded | [6 empty] | 1.3- Configure CORS properly
| SEC-017 | No Secrets Management Solution | [6 empty] | 1.4- Implement basic rate limiting
1.2 | BUGS-SA-012 | React Query Cache Not Parameterized by Trip Inputs | [6 empty] | 1.5- Set up database connection pooling
| AWS-022 | MFA and key rotation gaps in IAM users | [6 empty] | 1.6- AWS security hardening (IAM policies, security groups)
1.3 | SEC-005 | Permissive CORS Configuration |  |  | 2 | Framework Upgrades & Core Performance |  |  | 2.1- Django framework upgrades (both backends)
1.4 | SEC-006 | Ineffective Rate Limiting | [6 empty] | 2.2- Critical N+1 query fixes and database optimization
| SEC-024 | No Request Size Limits | [6 empty] | 2.3- Database indexing and migration work
| PERF-DB-021 | Missing Per-Endpoint Rate Limiting | [6 empty] | 2.4- Pagination improvements
| PERF-CR-001 | No API Rate Limiting |  |  | 3 | Authentication & Token Management |  |  | 3.1- Token lifecycle management (access + refresh tokens)
| BUGS-DB-010 | Missing Request Size Limits | [6 empty] | 3.2- httpOnly cookie implementation
| BUGS-MB-005 | Throttle Rates Set to 1000/min anon and 5000/sec user | [6 empty] | 3.3- CSRF protection
1.5 | PERF-DB-002 | Missing Database Connection Pooling | [6 empty] | 3.4- Multi-factor authentication (MFA)
| PERF-MB-005 | Duplicate FirebaseStorageProvider | [6 empty] | 3.5- Testing authentication flows
| PERF-MB-015 | No Database Connection Pooling |  |  | 4 | Performance Optimization |  |  | 4.1- Remaining N+1 query fixes
| PERF-MP-013 | No HTTP Client Configuration | [6 empty] | 4.2- Aggregation pipeline optimization
1.6 | AWS-010 | Security risk: port 22 (SSH) is open to the world on most EC2 instances. | [6 empty] | 4.3- Caching implementation
| AWS-011 | Database port is exposed to the internet (0.0.0.0/0) for EC2 i-0e935890cfd61f7c0. | [6 empty] | 4.4- Load testing and profiling
| AWS-013 | HTTP port 80 is open, allowing unencrypted public access. | [6 empty] | 4.5- Performance monitoring setup
| AWS-019 | CloudTrail management events disabled | [6 empty] | 4.5.a- Backend & API performance telemetry
| AWS-020 | External resource sharing via IAM Access Analyzer findings | [6 empty] | 4.5.b- Frontend & rendering performance monitoring
| AWS-026 | Application Load Balancers serving HTTP health checks | [6 empty] | 4.5.c- Error, security & compliance monitoring
| AWS-028 | Security Groups â€“ Unrestricted Access | [6 empty] | 4.5.d- Infrastructure & device-level monitoring
| AWS-029 | Application Load Balancer Security Group Misconfiguration |  |  | 5 | UI/UX & Mobile |  |  | 5.1- All UI/UX improvements (sharapp, dashboard, mobile apps)
WP2: Framework Upgrades & Core Performance | [8 empty] | 5.1.a- Accessibility & semantic structure
2.1 | SEC-010 | Outdated Django Framework | [6 empty] | 5.1.b- Visual design & theming
| PERF-DB-020 | No Query Monitoring | [6 empty] | 5.1.c- Navigation & user flows
| PERF-DB-024 | WhiteNoise for Static Files | [6 empty] | 5.1.d- Feedback, loading & status UX
| PERF-MB-014 | Missing Redis Cache Configuration | [6 empty] | 5.2- Mobile app bug fixes
2.2 | PERF-DB-001 | No Database Query Optimization | [6 empty] | 5.2.a- Mobile visual & theming defects
| PERF-DB-003 | N+1 Query in Account Serializer | [6 empty] | 5.2.b- Mobile layout & responsiveness issues
| PERF-DB-010 | Missing Query Optimization (only/defer) | [6 empty] | 5.2.c- Mobile UX & interaction bugs
| PERF-DB-011 | Inefficient Nested Loops Over QuerySets | [6 empty] | 5.3- Responsive design fixes
| PERF-DB-013 | Missing Indexes on Frequently Queried Fields | [6 empty] | 5.4- Cross-browser testing
| PERF-MB-002 | Missing Database Indexes |  |  | 6 | Bugs & Code Quality |  |  | 6.1- Perform code quality review and refactoring
| PERF-MB-003 | N+1 in Driver Transactions | [6 empty] | 6.2- Fix remaining bugs
2.3 | PERF-DB-005 | Inefficient Driver Pagination | [6 empty] | 6.2.a- API & integration bugs
| PERF-DB-012 | Complex Aggregation Pipeline | [6 empty] | 6.2.b- Security & compliance bugs
| PERF-DB-016 | Date Filtering Using ObjectId Only | [6 empty] | 6.2.c- State & performance bugs
| PERF-DB-018 | Unindexed Regex Queries | [6 empty] | 6.2.d- Error-handling & validation bugs
| PERF-MB-004 | Inefficient Driver Geographic Search | [6 empty] | 6.2.e- Build & tooling issues
| UIUX-SA-018 | Missing Favicon Fallbacks | [6 empty] | 6.3- Conduct final system testing and validation
| UIUX-SA-019 | No Language Attribute Fallback |  |  | 7 | Finalizing AWS &Documentation |  |  | 7.1- Optimize AWS resources (EC2, EBS, RDS)
| UIUX-MD-002 | Advertisement carousel never reaches last slide & leaks timer | [6 empty] | 7.2- Prepare documentation
| UIUX-DF-013 | No focus indicators
| UIUX-DF-030 | Inconsistent font sizes
| UIUX-DF-032 | Modal backdrop z-index issues
| UIUX-DF-037 | Print styles missing
| UIUX-DB-009 | Passenger pagination performs expensive regex on phone numbers
| BUGS-SA-014 | Duration & Distance Rows Assume Index 0 Always Exists
| BUGS-SA-021 | Unused CSS Class Definitions
| BUGS-DF-016 | No Privacy Policy Link
| BUGS-DB-015 | Missing Database Indexes
2.4 | PERF-DB-004 | Massive Aggregation Without Pagination
| PERF-DB-029 | No Pagination on Transaction Exports
| PERF-MB-010 | No Pagination on Trip Lists
| PERF-MP-011 | No Pagination in Trip History
| UIUX-MD-011 | No pagination or virtual scrolling in trip history
| UIUX-DF-004 | Unoptimized Firebase Queries
| UIUX-DB-001 | Driver pagination allows unbounded limit
| UIUX-DB-002 | GarageTrips endpoint lacks pagination
| UIUX-DB-007 | Driver pagination returns nested car/account blocks that break table layouts
| UIUX-DB-008 | Passenger pagination omits total counts so grid height jumps
| UIUX-DB-013 | Driver pagination lacks next or prev metadata
| UIUX-DB-019 | Passenger pagination returns raw ValueError traces
| BUGS-MD-006 | Pagination guard dereferences `totalTripsCount!` before it is set
WP3: Authentication & Token Management
3.1 | SEC-007 | Excessive Token Lifetime
| SEC-013 | Excessive OTP Validity Period
| SEC-022 | Unlimited Concurrent Sessions
| SEC-023 | Weak Password Policy
| PERF-DB-006 | Missing Caching Layer
| UIUX-MB-005 | Driver phone verification deletes accounts after OTP expiry
| UIUX-MB-006 | Driver username verification deletes profiles
| UIUX-MB-007 | Passenger phone verification mirrors the destructive delete pattern
| UIUX-MB-010 | OTP email locked to 600px with no media queries
| UIUX-MB-011 | OTP email uses generic blue palette
| UIUX-MB-012 | OTP digits spaced with 8px letter-spacing
| UIUX-MB-013 | OTP email lacks a primary action
| UIUX-MB-015 | OTP email relies on color alone to signal status
| UIUX-MB-017 | Passenger username verification returns raw 404 text
| UIUX-MB-022 | OTP email offers no support or escalation link
| UIUX-MB-023 | Hosted checkout inherits Mastercard theme
| UIUX-MB-024 | OTP template mixes inconsistent heading sizes
| UIUX-MB-025 | OTP email lacks RTL direction support
| UIUX-MB-026 | OTP header spacing assumes desktop margins
| UIUX-DB-005 | OTP validation deletes accounts after expiry
| UIUX-DB-018 | AuthTokenView logs users out mid session with generic 401
| BUGS-MD-010 | Token stored in plain SharedPreferences without encryption
| BUGS-MD-014 | Password validation regex allows weak passwords
| BUGS-DF-010 | No Session Timeout Implementation
| BUGS-DF-017 | No Cookie Consent Mechanism
| BUGS-DB-003 | Weak Password Policy
| BUGS-DB-004 | OTP Token Expiry Too Long
| BUGS-DB-005 | Insufficient Session Management
| BUGS-MB-003 | Driver Phone Verification Endpoint Enables Enumeration and Deletion
3.2 | SEC-008 | Authentication Tokens in localStorage
| BUGS-DF-009 | Language Selection Stored in localStorage Without Validation
3.3 | BUGS-DF-007 | No CSRF Protection Visible
| BUGS-DB-006 | Missing CSRF Token Validation
3.4 | SEC-009 | No Multi-Factor Authentication
WP4: Performance Optimization
4.1 | PERF-DB-009 | Excel Export Loads All Data Into Memory
| PERF-DB-015 | Missing Query Result Caching
| PERF-DB-017 | Print Statements in Production
| PERF-DB-019 | Large Serializer Depth
| PERF-DB-023 | No HTTP/2 Support Verification
| PERF-DB-030 | Redundant Serializer Database Queries
| PERF-DB-031 | Excessive Debug Print Statements
| PERF-MB-006 | Inefficient Promo Code Validation
| PERF-MB-007 | Redundant Trip Fetching in Celery
| PERF-MB-008 | No Caching for Country Settings
| PERF-MB-009 | Inefficient Token Validation
| PERF-MB-013 | Heavy Serialization Without Field Selection
| PERF-DF-008 | QueryClient Default Config
| PERF-NTH-002 | Implement Database Query Logging
| PERF-NTH-007 | Consider Read Replicas
4.2 | PERF-DB-025 | Unoptimized Trip Export Pipeline
| PERF-DB-028 | Inefficient Wallet Calculation
| PERF-NTH-006 | Set Up Load Testing Pipeline
4.3 | PERF-DB-014 | No Response Compression
| PERF-DB-022 | No CDN for Static/Media Files
| PERF-MB-001 | Blocking Synchronous Trip Assignment Loop
| PERF-MB-012 | Cache Pollution with Driver Attempts
| PERF-DF-012 | No Image Optimization
| PERF-MP-005 | No Image Caching Configuration
| PERF-MD-003 | Firebase Persistence Disabled
| PERF-MD-012 | Image Picker Without Compression
| PERF-CR-007 | No Compression
| PERF-NTH-008 | Implement Browser HTTP Caching Headers
| UIUX-SA-020 | No Cache-Busting for Static Assets
| UIUX-MP-024 | No Onboarding Completion Tracking Onboarding State Not Properly Tracked
| UIUX-MP-032 | No Onboarding Completion Tracking
| UIUX-MD-008 | Image cache never cleared during profile updates
| BUGS-MP-017 | Inconsistent Naming Conventions Mixed Naming Styles for Variables and Constants
| BUGS-MP-019 | DateTime Not Using Server Time Synchronization Using Device Time for Business Logic
| BUGS-MP-026 | DateTime Not Using Server Time Synchronization
| BUGS-MB-007 | Trip Creation Busy-Waits on Cache Without Timeout
4.4 | PERF-DB-007 | Synchronous File Upload in Request
| PERF-DB-008 | No Celery for Heavy Operations
| PERF-DB-026 | Synchronous SMS Sending
| PERF-DB-027 | Synchronous Firebase Operations
| PERF-MB-011 | Synchronous Firebase in Request Path
| PERF-MP-004 | Synchronous Hive Initialization
| PERF-MD-004 | Synchronous Wakelock in Main
| PERF-MD-010 | Firebase Messaging Blocks Startup
| PERF-MD-015 | Polyline on UI Thread
| PERF-SA-005 | Synchronous Geocoding Blocks UI
| PERF-CR-004 | No Load Testing
| PERF-NTH-005 | Implement App Startup Profiling
| UIUX-MD-004 | Face ID/Touch ID toggle never appears
4.5 | SEC-015 | Insufficient Logging and Monitoring
| PERF-SA-010 | Missing Performance Metrics
| PERF-CR-002 | Firebase Cost Risk
| PERF-CR-005 | No APM Tools
| PERF-NTH-001 | Add Application Performance Monitoring (APM)
| PERF-NTH-003 | Add Web Vitals Tracking
| UIUX-MP-023 | Missing Performance Monitoring No Production Performance Tracking
| UIUX-MP-031 | Missing Performance Monitoring
| UIUX-DF-015 | Missing Alt Text on Images
| BUGS-MP-007 | Unsafe Context Usage in Async Callbacks `BuildContext` Used Across Async Gaps
| BUGS-DB-007 | No Account Lockout Mechanism
WP5: UI/UX & Mobile
5.1 | UIUX-SA-002 | Missing Loading States for Payment Link Creation
| UIUX-SA-003 | Missing rel Attributes on External Links
| UIUX-SA-006 | Poor contrast on status badges
| UIUX-SA-008 | Missing alt text for images
| UIUX-SA-011 | No keyboard shortcuts
| UIUX-SA-012 | Inconsistent component styling
| UIUX-SA-014 | No loading progress indicator
| UIUX-SA-015 | Inconsistent date formats
| UIUX-SA-017 | Inactive state unclear
| UIUX-SA-021 | Multiple loading states
| UIUX-SA-022 | Pixelated avatar images
| UIUX-SA-023 | Header logo cut off
| UIUX-SA-024 | No breadcrumbs
| UIUX-SA-025 | Button sizes inconsistent
| UIUX-SA-026 | No skip navigation
| UIUX-DF-002 | No Code Splitting for Routes
| UIUX-DF-003 | Missing React.memo on Frequently Re-rendered Components
| UIUX-DF-005 | Large Number of State Updates in Render
| UIUX-DF-006 | Dashboard charts overflow on small screens
| UIUX-DF-008 | No keyboard navigation for data grids
| UIUX-DF-009 | Poor color contrast in dark sections
| UIUX-DF-011 | RTL layout broken for Arabic
| UIUX-DF-012 | Sidebar state lost on refresh
| UIUX-DF-014 | No Aria Labels on Interactive Elements
| UIUX-DF-016 | No Focus Management After Modal Close
| UIUX-DF-017 | Hardcoded Strings Not Internationalized
| UIUX-DF-018 | No Empty States for Data Grids
| UIUX-DF-019 | Error Messages Too Technical
| UIUX-DF-020 | Inconsistent Button Disabled States
| UIUX-DF-021 | Inconsistent Date Formatting
| UIUX-DF-023 | Inconsistent button styles
| UIUX-DF-024 | Three different loading spinners
| UIUX-DF-025 | Table columns misaligned with headers
| UIUX-DF-026 | No breadcrumb navigation
| UIUX-DF-027 | Missing ARIA labels
| UIUX-DF-028 | Status colors not colorblind safe
| UIUX-DF-031 | Mixed icon libraries
| UIUX-DF-033 | Deep links don't work
| UIUX-DF-034 | No Confirmation on Destructive Actions
| UIUX-DF-035 | Inconsistent spacing between sections
| UIUX-DF-038 | Brand colors inconsistent
| UIUX-DF-039 | Tooltip styles vary
| UIUX-MB-001 | Payment page renders an empty layout before the checkout iframe
| UIUX-MB-003 | Hosted checkout offers no visible cancel/back affordance
| UIUX-MB-004 | Checkout page lacks language, title, and instructions
| UIUX-MB-008 | AuthTokenView logs users out with "Invalid token" only
| UIUX-MB-014 | Error and cancel callbacks only log to console
| UIUX-MB-016 | Driver phone verification returns generic strings
| UIUX-MB-018 | Passenger email verification lacks fallback paths
| UIUX-MB-019 | Passenger login returns HTTP 422 with no guidance
| UIUX-MB-020 | Trip creation returns bare string when no drivers available
| UIUX-MB-021 | Checkout markup lacks skeleton loader or progress indicator
| UIUX-DB-003 | Transaction claim endpoint responds with plain OK
| UIUX-DB-004 | Checkout template misses lang, title, and labels
| UIUX-DB-006 | Transaction claim logging happens after the database update
| UIUX-DB-011 | Push notifications skip severity mapping
| UIUX-DB-012 | Notification copy mixes sentence case and uppercase IDs
| UIUX-DB-014 | Passenger search returns HTTP 200 with string Not Found
| UIUX-DB-015 | Error and cancel callbacks log to console instead of surfacing UI feedback
| UIUX-DB-016 | SMS encoder drops fallback language metadata
| UIUX-DB-017 | Dashboard login gives identical errors for deleted and suspended users
| UIUX-DB-020 | GarageTrips requires magic filter_type numbers with no descriptors
| UIUX-DB-021 | TripInfoView returns ungrouped fare details
| UIUX-DB-022 | Driver wallet export reorders columns server side
| UIUX-DB-023 | Schedule trip reminders mix Arabic and English without locale tokens
| UIUX-DB-024 | SMS templates omit JTNY branding
| UIUX-DB-025 | Excel exports use default serif fonts
| UIUX-DB-026 | Auth error responses reuse backend exception text
5.2 | UIUX-MP-001 | Map search bar covers location pin
| UIUX-MP-002 | Stuck in loading screen
| UIUX-MP-003 | Hardcoded Serving Areas Instead of API Response
| UIUX-MP-004 | No Offline Handling or Network State Management
| UIUX-MP-006 | No loading state during booking
| UIUX-MP-007 | Color-only status indicators
| UIUX-MP-008 | Driver info card blocks map
| UIUX-MP-009 | RTL layout broken
| UIUX-MP-010 | Insufficient contrast
| UIUX-MP-011 | Lack of Const Constructors Missing `const` Keywords on Immutable Widgets
| UIUX-MP-012 | Hardcoded Strings Not Using Localization
| UIUX-MP-013 | Misaligned car class images
| UIUX-MP-014 | Three different modal styles
| UIUX-MP-016 | Buttons too small
| UIUX-MP-017 | Overlapping price estimates
| UIUX-MP-018 | Deep link handling broken
| UIUX-MP-019 | Inconsistent Color Usage Colors Not Consistently Using Theme
| UIUX-MP-020 | No Haptic Feedback Missing Tactile Feedback on Interactions
| UIUX-MP-021 | No Pull-to-Refresh Functionality Data Lists Cannot Be Refreshed by User
| UIUX-MP-022 | No Dark Mode Support Only Light Theme Implemented
| UIUX-MP-025 | Inconsistent Color Usage
| UIUX-MP-026 | No Haptic Feedback
| UIUX-MP-027 | Inconsistent Border Radius Values
| UIUX-MP-028 | No Code Splitting or Lazy Loading
| UIUX-MP-029 | No Pull-to-Refresh Functionality
| UIUX-MP-030 | No Dark Mode Support
| UIUX-MP-033 | Brand colors incorrect
| UIUX-MP-034 | Blurry icons on high DPI
| UIUX-MP-036 | Animation speeds vary
| UIUX-MP-037 | Receipt layout broken
| UIUX-MD-003 | Trip type displays placeholder text
| UIUX-MD-005 | Connectivity detection disabled everywhere
| UIUX-MD-006 | Trip request timer overflows progress indicator
| UIUX-MD-007 | No validation on OCR-scanned trip kilometer values
| UIUX-MD-009 | No loading state when switching wallet tabs
| UIUX-MD-010 | Trip request dialog shows accept button only
| UIUX-MD-012 | No feedback when biometric authentication fails to initialize
| UIUX-MD-013 | No offline mode indicators or queuing
| UIUX-MD-014 | SOS button accessible even when not in trip
| UIUX-MD-015 | Firestore listener not properly cleaned up on logout
| UIUX-MD-016 | No confirmation dialog when changing payment method
| UIUX-MD-017 | Trip request modal cuts off on small screens
| UIUX-MD-018 | Back button exits app unexpectedly
| UIUX-MD-019 | Status colors unclear
| UIUX-MD-021 | No voice navigation
| UIUX-MD-022 | Can't return from trip details
| UIUX-MD-023 | Missing empty states in wallet and trip history screens
| UIUX-MD-024 | No visual indication of trip request timeout countdown
| UIUX-MD-025 | Text too small for driving
| UIUX-MD-026 | Inconsistent iOS/Android UI
| UIUX-MD-027 | Earnings chart unreadable
| UIUX-MD-028 | Confusing tab navigation
| UIUX-MD-029 | Icon size variations
| UIUX-MD-031 | Night mode missing
| UIUX-MD-032 | Small touch targets
| UIUX-MD-033 | Overlapping elements in RTL
| UIUX-MD-034 | Unused imports and dependencies bloat APK size
| UIUX-MD-035 | Multiple button styles
| UIUX-MD-036 | Outdated Material Design
| UIUX-MD-037 | Profile image distorted
| UIUX-MD-038 | Font inconsistency
| BUGS-MP-001 | Missing Error Handling in API Helper
| BUGS-MP-002 | Potential setState After Dispose
| BUGS-MP-003 | Duplicate Provider Registration
| BUGS-MP-004 | Missing Input Validation and Sanitization Insufficient Client-Side Input Validation
| BUGS-MP-005 | Excessive Use of `print()` Statements Debug Print Statements in Production Code
| BUGS-MP-006 | Version Mismatch Between `pubspec.yaml` and `main.dart` Hardcoded Version String Doesn't Match Package Version
| BUGS-MP-008 | Unhandled Null Reference Exceptions Forced Unwrapping of Nullable Types
| BUGS-MP-009 | Missing Input Validation and Sanitization
| BUGS-MP-010 | Excessive Use of print() and debugPrint() Statements
| BUGS-MP-011 | Version Mismatch Between pubspec.yaml and main.dart
| BUGS-MP-012 | Unsafe Context Usage in Async Callbacks
| BUGS-MP-013 | Unhandled Null Reference Exceptions
| BUGS-MP-014 | Multiple TODO Comments Left in Production Code Incomplete Implementations Marked with TODO
| BUGS-MP-015 | Commented Out Code Blocks Large Blocks of Commented Code in Source Files
| BUGS-MP-016 | Magic Numbers Throughout Codebase Hardcoded Numeric Values Without Named Constants
| BUGS-MP-018 | Large Widget Build Methods Build Methods Exceeding 500 Lines
| BUGS-MP-020 | Multiple TODO Comments Left in Production Code
| BUGS-MP-021 | Commented Out Code Blocks
| BUGS-MP-022 | Magic Numbers Throughout Codebase
| BUGS-MP-023 | Empty Catch Blocks Swallowing Exceptions
| BUGS-MP-024 | Lack of Const Constructors
| BUGS-MP-025 | Large Widget Build Methods
| BUGS-MP-027 | Unused Import Statements Imported Packages Not Used in File
| BUGS-MP-028 | Missing Documentation Comments No Dartdoc Comments on Public APIs
| BUGS-MP-029 | Inconsistent File Naming Directory Name Typo and Inconsistent File Naming
| BUGS-MP-030 | Unused Variables and Parameters Variables Declared But Never Used
| BUGS-MP-031 | Inconsistent Async/Await Pattern Mixing `.then()` and `async/await` Styles
| BUGS-MP-032 | Unused Import Statements
| BUGS-MP-033 | Missing Documentation Comments
| BUGS-MP-034 | Inconsistent File Naming
| BUGS-MP-035 | Unused Variables and Parameters
| BUGS-MP-036 | Inconsistent Async/Await Pattern
| BUGS-MD-001 | Race condition in Firebase user data initialization
| BUGS-MD-002 | Background push handler never processes payload
| BUGS-MD-003 | Notification listeners multiply on every tap
| BUGS-MD-004 | Map initialization ignores denied permissions
| BUGS-MD-005 | Background location never switched off
| BUGS-MD-007 | Account deletion hidden on Android
| BUGS-MD-008 | Notification handler assumes `message.notification` is always present
| BUGS-MD-009 | Wallet calculation double-counts unclaimed transactions
| BUGS-MD-011 | Excessive debug logging exposes sensitive data
| BUGS-MD-012 | Map screen shows hardcoded Arabic text regardless of locale
| BUGS-MD-013 | Location stream never disposed properly
| BUGS-MD-015 | Missing privacy policy acknowledgment on data collection
| BUGS-MD-016 | Unchecked null dereference in notification handlers
| BUGS-MD-017 | Trip history loaders never recover from failures
| BUGS-MD-018 | Transaction ID display logic will crash on short UUIDs
| BUGS-MD-019 | Memory leak from Timer in advertisement widget
| BUGS-MD-020 | Dio timeout configuration insufficient for poor networks
5.3 | UIUX-SA-001 | Trip info cards overflow viewport
| UIUX-SA-004 | Mobile view map unusable
| UIUX-SA-007 | Map doesn't resize dynamically
| UIUX-SA-009 | Poor Responsive Design for Map Height
| UIUX-SA-010 | Inconsistent Spacing and Padding
| UIUX-SA-013 | Download links overlap footer
| UIUX-SA-016 | Text truncation issues
| UIUX-MP-005 | Payment methods cut off on SE models
| UIUX-MP-015 | Time picker unusable in landscape
| UIUX-MP-035 | Rating stars too close
| UIUX-MD-001 | Map controls overlap trip info
| UIUX-MD-020 | Chat keyboard covers input
| UIUX-MD-030 | Landscape mode broken
| UIUX-DF-001 | Mobile view completely broken
| UIUX-DF-010 | Map doesn't resize with viewport
| UIUX-DF-022 | Mobile Responsiveness Issues
| UIUX-DF-029 | Horizontal scroll on medium screens
| UIUX-DF-036 | Footer overlaps content
| UIUX-MB-002 | Checkout page missing viewport meta
| UIUX-DB-010 | Driver wallet export blocks request thread
| UIUX-SA-005 | No back navigation option
| UIUX-DF-007 | Back button doesn't work with HashRouter
| UIUX-MB-009 | No document title or branding on checkout page
WP6: Bugs & Code Quality
6.1 | BUGS-SA-005 | Weak Comparison Operators
| BUGS-SA-008 | Hardcoded Currency Symbol
| BUGS-SA-015 | Commented Code in Production
| BUGS-SA-017 | Inconsistent Function Declaration Syntax
| BUGS-SA-020 | Magic Numbers in Code
| BUGS-SA-022 | Incomplete ESLint Configuration
| BUGS-SA-024 | Mixed Quoting Styles
| BUGS-DF-024 | Inconsistent Import Organization
| BUGS-DF-025 | TODO Comments Without Context
| BUGS-DF-026 | Magic Numbers Throughout Code
| BUGS-DF-027 | No PropTypes or TypeScript
| BUGS-DF-028 | Inconsistent File Naming
| BUGS-MB-008 | clean_drivers_data Zips Unrelated Firestore Collections
6.2 | SEC-011 | Missing Security Headers
| SEC-012 | Insufficient Input Validation
| SEC-014 | Debug Mode Enabled
| SEC-016 | No Web Application Firewall
| SEC-018 | No API Versioning
| SEC-019 | No SSL Certificate Pinning
| SEC-020 | No Root/Jailbreak Detection
| SEC-021 | Insufficient File Upload Validation
| SEC-026 | No Content Security for Stored Files
| PERF-DF-001 | Insufficient Code Splitting
| PERF-DF-002 | Heavy Dependencies
| PERF-DF-003 | No Lazy Loading for Routes
| PERF-DF-004 | Large MUI Bundle Without Tree-Shaking
| PERF-DF-005 | Excessive useState/useEffect Usage
| PERF-DF-006 | Missing React.memo
| PERF-DF-007 | Context Providers Without Memoization
| PERF-DF-009 | No Request Deduplication
| PERF-DF-010 | Firebase Listeners Without Cleanup
| PERF-DF-011 | Large DataGrid Without Virtualization
| PERF-DF-013 | Duplicate Charting Libraries
| PERF-DF-014 | High Chunk Size Warning Limit
| PERF-DF-015 | No Build-Time Env Optimization
| PERF-MP-001 | Too Many Root Providers
| PERF-MP-002 | Duplicate FirebaseStorageProvider
| PERF-MP-003 | Missing const Constructors
| PERF-MP-006 | Heavy Dependencies
| PERF-MP-007 | No Lazy Loading of Maps
| PERF-MP-008 | Multiple Location Services
| PERF-MP-009 | Provider Without Selective Rebuilds
| PERF-MP-010 | Firestore Persistence Enabled
| PERF-MP-012 | Flutter HTML in Chat
| PERF-MP-014 | Videos in Assets
| PERF-MD-001 | MapProvider Eager Initialization
| PERF-MD-002 | 14 Root ChangeNotifierProviders
| PERF-MD-005 | Old SDK Version
| PERF-MD-006 | Audio Player Resource Leak
| PERF-MD-007 | Heavy Dependency Overrides
| PERF-MD-008 | Google MLKit Text Recognition
| PERF-MD-009 | Unoptimized Location Tracking
| PERF-MD-011 | Dio Without Caching/Retry
| PERF-MD-013 | Device Preview in Production
| PERF-MD-014 | Google Maps Without Lite Mode
| PERF-SA-001 | No Loading States
| PERF-SA-002 | Firebase Listener Memory Leak
| PERF-SA-003 | Google Maps Re-initialization
| PERF-SA-004 | No Error Boundaries
| PERF-SA-006 | No API Response Caching
| PERF-SA-007 | Firebase Bundle Not Optimized
| PERF-SA-008 | Map Loads Unnecessarily
| PERF-SA-009 | No Request Debouncing
| PERF-SA-011 | No SSR or Progressive Enhancement
| PERF-SA-012 | Zero Test Coverage
| PERF-CR-003 | No Global Caching Strategy
| PERF-CR-006 | No Performance Budgets
| PERF-NTH-004 | Implement HTTP/2 Server Push
| PERF-NTH-009 | Add Prefetching for Next Pages
| PERF-NTH-010 | Implement Adaptive Image Loading
| BUGS-SA-001 | Missing Dependencies in Package.json
| BUGS-SA-002 | Unsafe Type Assertion with Non-null Assertion Operator
| BUGS-SA-003 | Unhandled Promise Rejection in Geocoder
| BUGS-SA-004 | Missing Image Path Leading Slash
| BUGS-SA-006 | No Error Boundary Implementation
| BUGS-SA-007 | Incomplete Error Handling in API Calls
| BUGS-SA-009 | Map Crashes When Destination Coordinates Are Missing
| BUGS-SA-010 | Weak Key Generation in Lists
| BUGS-SA-011 | Missing TypeScript Strict Mode Enforcement
| BUGS-SA-013 | Duplicate Firestore Listeners from Header + Page
| BUGS-SA-016 | Console Error in Production Code
| BUGS-SA-018 | Missing PropTypes or Runtime Validation
| BUGS-SA-019 | Unused Import Statement
| BUGS-SA-023 | Unused Statement in useEffect
| BUGS-SA-025 | No TypeScript Interfaces for API Responses
| BUGS-DF-001 | No Error Boundary Implementation
| BUGS-DF-002 | Race Condition in Chat Message Loading
| BUGS-DF-003 | Memory Leak: Event Listeners Not Cleaned Up
| BUGS-DF-004 | Unhandled Promise Rejections
| BUGS-DF-005 | Insecure Password Reset Flow
| BUGS-DF-006 | Weak Password Requirements
| BUGS-DF-008 | Hardcoded API URLs in Chat
| BUGS-DF-011 | Axios Interceptor Initialized Multiple Times
| BUGS-DF-012 | Dependency Array Issues in useEffect
| BUGS-DF-013 | Improper Error Message Construction
| BUGS-DF-014 | Commented Out Critical Code
| BUGS-DF-015 | No Loading States for Async Operations
| BUGS-DF-018 | No Data Export Functionality
| BUGS-DF-019 | Missing Input Length Validation
| BUGS-DF-020 | Source Maps Enabled in Production
| BUGS-DF-021 | Incorrect Type Checking
| BUGS-DF-022 | Potential Null Reference Errors
| BUGS-DF-023 | Duplicate Package Managers
| BUGS-DF-029 | No Account Deletion Option
| BUGS-DB-001 | Firebase Private Key Exposed
| BUGS-DB-002 | DEBUG Mode Enabled in Dev
| BUGS-DB-009 | Missing Audit Logging for Sensitive Operations
| BUGS-DB-011 | Commented Out Code
| BUGS-DB-012 | Excessive Exception Handling with Print
| BUGS-DB-014 | Inconsistent Naming Conventions
| BUGS-MB-001 | TripDrivePassengerView Is World-Readable
| BUGS-MB-002 | Legacy settings.py.save Leaks SECRET_KEY and Debug Defaults
| BUGS-MB-004 | Passenger Email Verification Endpoint is Anonymous and Destructive
| BUGS-MB-006 | Payment Callback Endpoints Dump Query Strings to Logs
6.3 | BUGS-DB-008 | PyJWT Version Vulnerability
| BUGS-DB-013 | Requests Version Missing Security Patches
WP7: Finalizing AWS & Documentation
7.1 | AWS-001 | The EC2 instance i-01d9d8b30a74fae1b (mobile) is over provisioned.
| AWS-002 | The EC2 instance i-0eb1bbd45ea19979e (live2) is over provisioned.
| AWS-003 | The EC2 instance i-0e935890cfd61f7c0 (live) is mis-sized.
| AWS-004 | The EC2 instance i-0520151b34ebc5ef6 (staging-mobile) is over provisioned.
| AWS-005 | The EC2 instance i-076e8ec11457150f6 (live2-front-staging) is over provisioned.
| AWS-006 | The EC2 instance i-0d1ebd56f4b6b206c (recover-test) is over provisioned.
| AWS-007 | Over provisioned EC2 resources make up ~71.4% of October 2025 cost.
| AWS-008 | Too many EBS volume snapshots are retained, including very old copies.
| AWS-009 | No consistent time slot is defined between backups.
| AWS-012 | AWS Cost Optimization Hub is disabled.
| AWS-014 | Low and inconsistent network activity indicates over-provisioned capacity.
| AWS-015 | CPU utilization stays mostly under 10%.
| AWS-016 | Memory usage averages below 10%.
| AWS-017 | Very low read/write operations suggest over-provisioned storage.
| AWS-018 | “Over-provisioned” status across all key metrics.
| AWS-021 | Unmanaged EBS/RDS snapshot lifecycle
| AWS-023 | Unassociated Elastic IP addresses
| AWS-024 | Underutilized Amazon EBS volumes
| AWS-025 | Missing Savings Plan / RI coverage
| AWS-027 | Reserved Instance optimization warnings